## Schedule
Phase | Task ID | Task Name | Workstream | Start | Finish | Duration (days) | % Complete | Baseline Start | Baseline Finish | Finish Variance (days) | Predecessors | Milestone Type | Owner | Budget ($) | Status
01 Initiation and Planning | ATL-101 | Project charter and business case | PMO | 2026-03-02 | 2026-03-16 | 14 | 100 | 2026-03-02 | 2026-03-16 | 0 |  |  | D. Okafor | 21000 | Complete
01 Initiation and Planning | ATL-102 | Charter approved | PMO | 2026-03-16 | 2026-03-16 | 0 | 100 | 2026-03-16 | 2026-03-16 | 0 | ATL-101 | Approval | D. Okafor | 0 | Complete
01 Initiation and Planning | ATL-103 | ERP vendor selection and contract negotiation | PMO | 2026-03-09 | 2026-05-04 | 56 | 100 | 2026-03-09 | 2026-04-20 | 14 | ATL-101SS+7 |  | D. Okafor | 88000 | Complete
01 Initiation and Planning | ATL-104 | Implementation contract signed | PMO | 2026-05-04 | 2026-05-04 | 0 | 100 | 2026-04-20 | 2026-04-20 | 14 | ATL-103 | Contract | D. Okafor | 0 | Complete
01 Initiation and Planning | ATL-105 | Project plan, WBS and schedule baseline | PMO | 2026-03-16 | 2026-04-06 | 21 | 100 | 2026-03-16 | 2026-04-06 | 0 | ATL-102 |  | T. Nguyen | 31500 | Complete
01 Initiation and Planning | ATL-106 | Governance and steering committee setup | PMO | 2026-03-16 | 2026-03-30 | 14 | 100 | 2026-03-16 | 2026-03-30 | 0 | ATL-102 |  | T. Nguyen | 21000 | Complete
01 Initiation and Planning | ATL-107 | Program mobilization and team onboarding | PMO | 2026-05-04 | 2026-05-25 | 21 | 100 | 2026-04-20 | 2026-05-11 | 14 | ATL-104, ATL-105 |  | D. Okafor | 31500 | Complete
01 Initiation and Planning | ATL-108 | Communication plan and stakeholder map | Change and Training | 2026-03-30 | 2026-04-13 | 14 | 100 | 2026-03-30 | 2026-04-13 | 0 | ATL-106 |  | L. Brooks | 21000 | Complete
01 Initiation and Planning | ATL-109 | As-is process inventory | PMO | 2026-03-23 | 2026-04-13 | 21 | 100 | 2026-03-23 | 2026-04-20 | -7 | ATL-105SS+7 |  | T. Nguyen | 42000 | Complete
01 Initiation and Planning | ATL-110 | Infrastructure requirements and sizing | Infrastructure | 2026-05-04 | 2026-05-25 | 21 | 100 | 2026-04-20 | 2026-05-11 | 14 | ATL-104 |  | K. Novak | 38000 | Complete
01 Initiation and Planning | ATL-111 | Risk and issue register established | PMO | 2026-03-30 | 2026-04-06 | 7 | 100 | 2026-03-30 | 2026-04-06 | 0 | ATL-106 |  | T. Nguyen | 10500 | Complete
01 Initiation and Planning | ATL-112 | Project kickoff | PMO | 2026-05-25 | 2026-05-25 | 0 | 100 | 2026-05-11 | 2026-05-11 | 14 | ATL-107, ATL-108 | Gate | D. Okafor | 0 | Complete
02 Design | ATL-201 | Finance process design workshops | Finance | 2026-05-25 | 2026-07-13 | 49 | 100 | 2026-05-11 | 2026-06-22 | 21 | ATL-112 |  | M. Chen | 92500 | Complete
02 Design | ATL-202 | Supply chain process design workshops | Supply Chain | 2026-05-25 | 2026-07-06 | 42 | 100 | 2026-05-11 | 2026-06-22 | 14 | ATL-112 |  | R. Alvarez | 92500 | Complete
02 Design | ATL-203 | HR and payroll process design workshops | HR and Payroll | 2026-05-25 | 2026-06-29 | 35 | 100 | 2026-05-11 | 2026-06-15 | 14 | ATL-112 |  | S. Patel | 66500 | Complete
02 Design | ATL-204 | Chart of accounts and organizational structure design | Finance | 2026-06-08 | 2026-07-06 | 28 | 100 | 2026-05-25 | 2026-06-22 | 14 | ATL-201SS+14 |  | M. Chen | 61500 | Complete
02 Design | ATL-205 | Item master and warehouse design | Supply Chain | 2026-06-08 | 2026-07-06 | 28 | 100 | 2026-05-25 | 2026-06-22 | 14 | ATL-202SS+14 |  | R. Alvarez | 61500 | Complete
02 Design | ATL-206 | Position and pay structure design | HR and Payroll | 2026-06-08 | 2026-06-29 | 21 | 100 | 2026-05-25 | 2026-06-15 | 14 | ATL-203SS+14 |  | S. Patel | 40000 | Complete
02 Design | ATL-207 | Integration architecture and interface catalog | Integration | 2026-05-25 | 2026-07-09 | 45 | 100 | 2026-05-11 | 2026-06-15 | 24 | ATL-112 |  | A. Rivera | 91000 | Complete
02 Design | ATL-208 | Data migration strategy and field mapping | Data Migration | 2026-05-25 | 2026-06-29 | 35 | 100 | 2026-05-11 | 2026-06-15 | 14 | ATL-109, ATL-112 |  | J. Nakamura | 70000 | Complete
02 Design | ATL-209 | Security roles and authorization design | Infrastructure | 2026-06-15 | 2026-07-13 | 28 | 100 | 2026-05-25 | 2026-06-22 | 21 | ATL-207SS+14, ATL-201FF |  | K. Novak | 50500 | Complete
02 Design | ATL-210 | Reporting and analytics requirements | Finance | 2026-07-06 | 2026-07-27 | 21 | 100 | 2026-06-22 | 2026-07-13 | 14 | ATL-204 |  | M. Chen | 46000 | Complete
02 Design | ATL-211 | Environment landscape design | Infrastructure | 2026-05-25 | 2026-06-08 | 14 | 100 | 2026-05-11 | 2026-05-25 | 14 | ATL-110 |  | K. Novak | 25000 | Complete
02 Design | ATL-212 | Conference room pilot | Finance | 2026-07-06 | 2026-07-27 | 21 | 100 | 2026-06-22 | 2026-07-13 | 14 | ATL-204, ATL-205, ATL-206 |  | M. Chen | 46000 | Complete
02 Design | ATL-213 | Fit-gap analysis and RICEFW inventory | PMO | 2026-07-27 | 2026-08-17 | 21 | 100 | 2026-07-13 | 2026-08-03 | 14 | ATL-212, ATL-111 |  | D. Okafor | 31500 | Complete
02 Design | ATL-214 | Design sign-off | PMO | 2026-08-17 | 2026-08-17 | 0 | 100 | 2026-08-03 | 2026-08-03 | 14 | ATL-213, ATL-207, ATL-208, ATL-209 | Gate | D. Okafor | 0 | Complete
03 Build and Configuration | ATL-301 | Development environment provisioning | Infrastructure | 2026-06-08 | 2026-06-29 | 21 | 100 | 2026-05-25 | 2026-06-15 | 14 | ATL-211 |  | K. Novak | 83000 | Complete
03 Build and Configuration | ATL-302 | Quality and production environments provisioning | Infrastructure | 2026-06-22 | 2026-07-20 | 28 | 100 | 2026-06-08 | 2026-07-06 | 14 | ATL-301SS+14 |  | K. Novak | 200500 | Complete
03 Build and Configuration | ATL-303 | Finance configuration: GL, AP and AR | Finance | 2026-08-17 | 2026-10-26 | 70 | 80 | 2026-08-03 | 2026-09-28 | 28 | ATL-214, ATL-301 |  | M. Chen | 123000 | In progress - behind
03 Build and Configuration | ATL-304 | Finance configuration: fixed assets and cash | Finance | 2026-08-31 | 2026-10-05 | 35 | 100 | 2026-08-17 | 2026-09-21 | 14 | ATL-303SS+14 |  | M. Chen | 77000 | Complete
03 Build and Configuration | ATL-305 | Supply chain configuration: procurement and inventory | Supply Chain | 2026-08-17 | 2026-10-05 | 49 | 100 | 2026-08-03 | 2026-09-28 | 7 | ATL-214, ATL-301 |  | R. Alvarez | 123000 | Complete
03 Build and Configuration | ATL-306 | Supply chain configuration: production and MRP | Supply Chain | 2026-08-31 | 2026-10-12 | 42 | 100 | 2026-08-17 | 2026-09-28 | 14 | ATL-305SS+14 |  | R. Alvarez | 92500 | Complete
03 Build and Configuration | ATL-307 | HR configuration: core HR and benefits | HR and Payroll | 2026-08-17 | 2026-09-28 | 42 | 100 | 2026-08-03 | 2026-09-14 | 14 | ATL-214, ATL-301 |  | S. Patel | 80000 | Complete
03 Build and Configuration | ATL-308 | Payroll configuration and tax setup | HR and Payroll | 2026-08-31 | 2026-10-19 | 49 | 90 | 2026-08-17 | 2026-09-28 | 21 | ATL-307SS+14 |  | S. Patel | 80000 | In progress - on track
03 Build and Configuration | ATL-309 | Security role build and testing | Infrastructure | 2026-07-13 | 2026-08-10 | 28 | 100 | 2026-06-22 | 2026-07-20 | 21 | ATL-209, ATL-301 |  | K. Novak | 50500 | Complete
03 Build and Configuration | ATL-310 | Report and dashboard development | Finance | 2026-09-14 | 2026-11-02 | 49 | 60 | 2026-08-24 | 2026-10-05 | 28 | ATL-210, ATL-303FF+7 |  | M. Chen | 92500 | In progress - on track
03 Build and Configuration | ATL-311 | Custom development: RICEFW objects | Integration | 2026-08-17 | 2026-11-09 | 84 | 65 | 2026-08-03 | 2026-10-05 | 35 | ATL-213, ATL-301 |  | A. Rivera | 164000 | In progress - behind
03 Build and Configuration | ATL-312 | Workflow and approval configuration | Finance | 2026-08-31 | 2026-09-21 | 21 | 100 | 2026-08-17 | 2026-09-07 | 14 | ATL-303SS+14 |  | M. Chen | 46000 | Complete
03 Build and Configuration | ATL-313 | Unit testing: finance | Finance | 2026-10-05 | 2026-10-19 | 14 | 85 | 2026-09-21 | 2026-10-05 | 14 | ATL-304, ATL-312 |  | M. Chen | 31000 | In progress - ahead
03 Build and Configuration | ATL-314 | Unit testing: supply chain | Supply Chain | 2026-10-12 | 2026-10-26 | 14 | 35 | 2026-09-28 | 2026-10-12 | 14 | ATL-306 |  | R. Alvarez | 31000 | In progress - ahead
03 Build and Configuration | ATL-315 | Unit testing: HR and payroll | HR and Payroll | 2026-10-19 | 2026-11-02 | 14 | 0 | 2026-09-28 | 2026-10-12 | 21 | ATL-308 |  | S. Patel | 26500 | Not started
03 Build and Configuration | ATL-316 | Build complete | PMO | 2026-11-09 | 2026-11-09 | 0 | 0 | 2026-10-12 | 2026-10-12 | 28 | ATL-313, ATL-314, ATL-315, ATL-311 | Gate | D. Okafor | 0 | Not started
04 Data Migration | ATL-401 | Data cleansing: customers and vendors | Data Migration | 2026-06-29 | 2026-08-24 | 56 | 100 | 2026-06-15 | 2026-07-27 | 28 | ATL-208 |  | J. Nakamura | 84000 | Complete
04 Data Migration | ATL-402 | Data cleansing: items and bills of material | Data Migration | 2026-06-08 | 2026-07-20 | 42 | 100 | 2026-05-25 | 2026-07-06 | 14 | ATL-208SS+14 |  | J. Nakamura | 84000 | Complete
04 Data Migration | ATL-403 | Data cleansing: employees and positions | HR and Payroll | 2026-06-08 | 2026-07-06 | 28 | 100 | 2026-05-25 | 2026-06-22 | 14 | ATL-208SS+14 |  | S. Patel | 53000 | Complete
04 Data Migration | ATL-404 | Migration tooling and ETL build | Data Migration | 2026-06-29 | 2026-08-10 | 42 | 100 | 2026-06-15 | 2026-07-20 | 21 | ATL-208, ATL-301 |  | J. Nakamura | 70000 | Complete
04 Data Migration | ATL-405 | Mock migration 1 | Data Migration | 2026-08-24 | 2026-09-07 | 14 | 100 | 2026-07-27 | 2026-08-10 | 28 | ATL-404, ATL-401, ATL-402, ATL-403 |  | J. Nakamura | 28000 | Complete
04 Data Migration | ATL-406 | Data reconciliation and defect fixing | Data Migration | 2026-09-07 | 2026-09-28 | 21 | 100 | 2026-08-10 | 2026-08-31 | 28 | ATL-405, ATL-410 |  | J. Nakamura | 42000 | Complete
04 Data Migration | ATL-407 | Mock migration 2 | Data Migration | 2026-11-09 | 2026-11-23 | 14 | 0 | 2026-10-12 | 2026-10-26 | 28 | ATL-406, ATL-316 |  | J. Nakamura | 28000 | Not started
04 Data Migration | ATL-408 | Mock migration 3: cutover rehearsal | Data Migration | 2027-01-25 | 2027-02-08 | 14 | 0 | 2026-12-28 | 2027-01-11 | 28 | ATL-407, ATL-604 |  | J. Nakamura | 28000 | Not started
04 Data Migration | ATL-409 | Data validation sign-off | Data Migration | 2027-02-08 | 2027-02-08 | 0 | 0 | 2027-01-11 | 2027-01-11 | 28 | ATL-408 | Approval | J. Nakamura | 0 | Not started
04 Data Migration | ATL-410 | Opening balances and open transactions strategy | Finance | 2026-07-06 | 2026-07-27 | 21 | 100 | 2026-06-22 | 2026-07-13 | 14 | ATL-204 |  | M. Chen | 46000 | Complete
05 Integration | ATL-501 | Interface development: bank and payment files | Integration | 2026-07-09 | 2026-08-13 | 35 | 100 | 2026-06-15 | 2026-07-20 | 24 | ATL-207, ATL-301 |  | A. Rivera | 91000 | Complete
05 Integration | ATL-502 | Interface development: CRM and e-commerce | Integration | 2026-07-23 | 2026-09-03 | 42 | 100 | 2026-06-29 | 2026-08-10 | 24 | ATL-501SS+14 |  | A. Rivera | 109000 | Complete
05 Integration | ATL-503 | Interface development: warehouse automation | Integration | 2026-08-06 | 2026-09-17 | 42 | 100 | 2026-07-13 | 2026-08-24 | 24 | ATL-502SS+14 |  | A. Rivera | 109000 | Complete
05 Integration | ATL-504 | Interface development: payroll provider and benefits carriers | HR and Payroll | 2026-09-28 | 2026-10-26 | 28 | 70 | 2026-09-14 | 2026-10-12 | 14 | ATL-207, ATL-307 |  | S. Patel | 53000 | In progress - ahead
05 Integration | ATL-505 | Middleware setup and monitoring | Infrastructure | 2026-07-20 | 2026-08-10 | 21 | 100 | 2026-07-06 | 2026-07-27 | 14 | ATL-302 |  | K. Novak | 68000 | Complete
05 Integration | ATL-506 | Interface unit testing | Integration | 2026-10-26 | 2026-11-16 | 21 | 0 | 2026-10-12 | 2026-11-02 | 14 | ATL-501, ATL-502, ATL-503, ATL-504, ATL-505 |  | A. Rivera | 54500 | Not started
05 Integration | ATL-507 | Integration build complete | Integration | 2026-11-16 | 2026-11-16 | 0 | 0 | 2026-11-02 | 2026-11-02 | 14 | ATL-506 | Gate | A. Rivera | 0 | Not started
05 Integration | ATL-508 | EDI trading partner onboarding | Supply Chain | 2026-11-16 | 2026-12-07 | 21 | 0 | 2026-11-02 | 2026-11-23 | 14 | ATL-507 |  | R. Alvarez | 46000 | Not started
05 Integration | ATL-509 | API security and penetration test | Infrastructure | 2027-01-04 | 2027-01-18 | 14 | 0 | 2026-12-07 | 2026-12-21 | 28 | ATL-603 |  | K. Novak | 25000 | Not started
06 Testing | ATL-601 | Test strategy and test case development | PMO | 2026-08-17 | 2026-09-21 | 35 | 100 | 2026-08-03 | 2026-09-07 | 14 | ATL-213 |  | T. Nguyen | 52500 | Complete
06 Testing | ATL-602 | Test environment setup and data load | Infrastructure | 2026-11-23 | 2026-12-07 | 14 | 0 | 2026-10-26 | 2026-11-09 | 28 | ATL-302, ATL-407, ATL-601, ATL-309 |  | K. Novak | 25000 | Not started
06 Testing | ATL-603 | System integration test cycle 1 | Integration | 2026-12-07 | 2027-01-04 | 28 | 0 | 2026-11-09 | 2026-12-07 | 28 | ATL-316, ATL-507, ATL-602, ATL-310 |  | A. Rivera | 73000 | Not started
06 Testing | ATL-604 | System integration test cycle 2 | Integration | 2027-01-04 | 2027-01-25 | 21 | 0 | 2026-12-07 | 2026-12-28 | 28 | ATL-603, ATL-508 |  | A. Rivera | 54500 | Not started
06 Testing | ATL-605 | Defect resolution and regression testing | Integration | 2027-01-11 | 2027-02-01 | 21 | 0 | 2026-12-14 | 2027-01-04 | 28 | ATL-604SS+7 |  | A. Rivera | 54500 | Not started
06 Testing | ATL-606 | User acceptance testing: finance | Finance | 2027-02-01 | 2027-03-01 | 28 | 0 | 2027-01-04 | 2027-02-01 | 28 | ATL-605 |  | M. Chen | 61500 | Not started
06 Testing | ATL-607 | User acceptance testing: supply chain | Supply Chain | 2027-02-01 | 2027-03-01 | 28 | 0 | 2027-01-04 | 2027-02-01 | 28 | ATL-605 |  | R. Alvarez | 61500 | Not started
06 Testing | ATL-608 | User acceptance testing: HR and payroll | HR and Payroll | 2027-02-01 | 2027-02-22 | 21 | 0 | 2027-01-04 | 2027-01-25 | 28 | ATL-605 |  | S. Patel | 40000 | Not started
06 Testing | ATL-609 | Performance and load testing | Infrastructure | 2027-01-25 | 2027-02-08 | 14 | 0 | 2026-12-28 | 2027-01-11 | 28 | ATL-604, ATL-509 |  | K. Novak | 25000 | Not started
06 Testing | ATL-610 | Payroll parallel run 1 | HR and Payroll | 2027-02-08 | 2027-02-22 | 14 | 0 | 2027-01-11 | 2027-01-25 | 28 | ATL-608SS+7 |  | S. Patel | 26500 | Not started
06 Testing | ATL-611 | Payroll parallel run 2 | HR and Payroll | 2027-02-22 | 2027-03-08 | 14 | 0 | 2027-01-25 | 2027-02-08 | 28 | ATL-610 |  | S. Patel | 26500 | Not started
06 Testing | ATL-612 | UAT defect fixes and retest | Integration | 2027-03-01 | 2027-03-15 | 14 | 0 | 2027-02-01 | 2027-02-15 | 28 | ATL-606, ATL-607, ATL-608 |  | A. Rivera | 36500 | Not started
06 Testing | ATL-613 | UAT exit and business sign-off | PMO | 2027-03-15 | 2027-03-15 | 0 | 0 | 2027-02-15 | 2027-02-15 | 28 | ATL-612, ATL-611, ATL-609 | Approval | D. Okafor | 0 | Not started
06 Testing | ATL-614 | Test completion report | PMO | 2027-03-15 | 2027-03-22 | 7 | 0 | 2027-02-15 | 2027-02-22 | 28 | ATL-613 |  | T. Nguyen | 10500 | Not started
07 Training and Change Management | ATL-701 | Change impact assessment | Change and Training | 2026-08-17 | 2026-09-14 | 28 | 100 | 2026-08-03 | 2026-08-31 | 14 | ATL-213 |  | L. Brooks | 42000 | Complete
07 Training and Change Management | ATL-702 | Role mapping and end-user list | Change and Training | 2026-09-14 | 2026-10-05 | 21 | 100 | 2026-08-31 | 2026-09-21 | 14 | ATL-701, ATL-209 |  | L. Brooks | 31500 | Complete
07 Training and Change Management | ATL-703 | Training needs analysis and curriculum | Change and Training | 2026-09-14 | 2026-10-05 | 21 | 100 | 2026-08-31 | 2026-09-21 | 14 | ATL-701 |  | L. Brooks | 31500 | Complete
07 Training and Change Management | ATL-704 | Training material development | Change and Training | 2026-11-09 | 2027-01-04 | 56 | 0 | 2026-10-12 | 2026-12-07 | 28 | ATL-703, ATL-316 |  | L. Brooks | 104000 | Not started
07 Training and Change Management | ATL-705 | Train-the-trainer sessions | Change and Training | 2027-01-04 | 2027-01-18 | 14 | 0 | 2026-12-07 | 2026-12-21 | 28 | ATL-704 |  | L. Brooks | 21000 | Not started
07 Training and Change Management | ATL-706 | End-user training wave 1: finance and procurement | Change and Training | 2027-02-01 | 2027-02-22 | 21 | 0 | 2027-01-04 | 2027-01-25 | 28 | ATL-705, ATL-605, ATL-709 |  | L. Brooks | 31500 | Not started
07 Training and Change Management | ATL-707 | End-user training wave 2: warehouse and production | Change and Training | 2027-02-08 | 2027-03-01 | 21 | 0 | 2027-01-11 | 2027-02-01 | 28 | ATL-706SS+7 |  | L. Brooks | 31500 | Not started
07 Training and Change Management | ATL-708 | End-user training wave 3: HR, payroll and self-service | Change and Training | 2027-02-15 | 2027-03-01 | 14 | 0 | 2027-01-18 | 2027-02-01 | 28 | ATL-707SS+7 |  | L. Brooks | 21000 | Not started
07 Training and Change Management | ATL-709 | Super-user network and support model | Change and Training | 2026-12-07 | 2027-01-04 | 28 | 0 | 2026-11-09 | 2026-12-07 | 28 | ATL-702, ATL-603SS |  | L. Brooks | 42000 | Not started
07 Training and Change Management | ATL-710 | Change readiness assessment | Change and Training | 2027-03-01 | 2027-03-15 | 14 | 0 | 2027-02-01 | 2027-02-15 | 28 | ATL-708, ATL-709 |  | L. Brooks | 21000 | Not started
07 Training and Change Management | ATL-711 | Training complete | Change and Training | 2027-03-15 | 2027-03-15 | 0 | 0 | 2027-02-15 | 2027-02-15 | 28 | ATL-710, ATL-712 | Gate | L. Brooks | 0 | Not started
07 Training and Change Management | ATL-712 | Quick reference guides and job aids | Change and Training | 2027-01-04 | 2027-01-25 | 21 | 0 | 2026-12-07 | 2026-12-28 | 28 | ATL-704 |  | L. Brooks | 31500 | Not started
08 Deployment and Hypercare | ATL-801 | Cutover plan and rehearsal | PMO | 2027-02-08 | 2027-03-08 | 28 | 0 | 2027-01-11 | 2027-02-08 | 28 | ATL-409, ATL-605 |  | D. Okafor | 42000 | Not started
08 Deployment and Hypercare | ATL-802 | Go/No-Go decision | PMO | 2027-03-22 | 2027-03-22 | 0 | 0 | 2027-02-22 | 2027-02-22 | 28 | ATL-614, ATL-711, ATL-801, ATL-609, ATL-409 | Gate | D. Okafor | 0 | Not started
08 Deployment and Hypercare | ATL-803 | Production cutover and final data load | Data Migration | 2027-03-22 | 2027-03-29 | 7 | 0 | 2027-02-22 | 2027-03-01 | 28 | ATL-802 |  | J. Nakamura | 29000 | Not started
08 Deployment and Hypercare | ATL-804 | Go-live | PMO | 2027-03-29 | 2027-03-29 | 0 | 0 | 2027-03-01 | 2027-03-01 | 28 | ATL-803 | Go-Live | D. Okafor | 0 | Not started
08 Deployment and Hypercare | ATL-805 | Hypercare support: weeks 1 to 4 | PMO | 2027-03-29 | 2027-04-26 | 28 | 0 | 2027-03-01 | 2027-03-29 | 28 | ATL-804 |  | D. Okafor | 42000 | Not started
08 Deployment and Hypercare | ATL-806 | Hypercare support: weeks 5 to 8 | PMO | 2027-04-26 | 2027-05-24 | 28 | 0 | 2027-03-29 | 2027-04-26 | 28 | ATL-805 |  | D. Okafor | 42000 | Not started
08 Deployment and Hypercare | ATL-807 | First month-end close in the new system | Finance | 2027-04-23 | 2027-05-03 | 10 | 0 | 2027-03-26 | 2027-04-05 | 28 | ATL-804FS+25 |  | M. Chen | 22000 | Not started
08 Deployment and Hypercare | ATL-808 | First payroll run in the new system | HR and Payroll | 2027-04-08 | 2027-04-15 | 7 | 0 | 2027-03-11 | 2027-03-18 | 28 | ATL-804FS+10 |  | S. Patel | 13500 | Not started
08 Deployment and Hypercare | ATL-809 | Post go-live performance tuning | Infrastructure | 2027-04-05 | 2027-04-19 | 14 | 0 | 2027-03-08 | 2027-03-22 | 28 | ATL-804FS+7 |  | K. Novak | 25000 | Not started
08 Deployment and Hypercare | ATL-810 | Legacy system decommissioning | Infrastructure | 2027-04-12 | 2027-04-26 | 14 | 0 | 2027-03-15 | 2027-03-29 | 28 | ATL-804FS+14 |  | K. Novak | 25000 | Not started
08 Deployment and Hypercare | ATL-811 | Hypercare exit | PMO | 2027-05-24 | 2027-05-24 | 0 | 0 | 2027-04-26 | 2027-04-26 | 28 | ATL-806, ATL-807, ATL-808, ATL-809 | Gate | D. Okafor | 0 | Not started
08 Deployment and Hypercare | ATL-812 | Lessons learned and benefits review | PMO | 2027-05-24 | 2027-06-14 | 21 | 0 | 2027-04-26 | 2027-05-17 | 28 | ATL-811 |  | T. Nguyen | 31500 | Not started
08 Deployment and Hypercare | ATL-813 | Project closeout | PMO | 2027-06-14 | 2027-06-14 | 0 | 0 | 2027-05-17 | 2027-05-17 | 28 | ATL-812, ATL-810 | Closeout | D. Okafor | 0 | Not started

## Field Mapping
Column | PowerGantt Lite data role | Required | Notes
Phase | Group | Optional | One grouping level; renders a summary bar per phase with expand/collapse
Task Name | Task Name | Required
Task ID | Task ID | Required when Predecessors are used | Unique per row
Predecessors | Predecessors | Optional | Comma-separated Task IDs with optional link type and lag in days: ATL-303SS+14, ATL-201FF, ATL-804FS+25. FS is assumed when no type is given
Start | Start Date | Required
Finish | Finish Date | Required
% Complete | % Complete | Optional | 0 to 100. Set the field to Don't summarize
Baseline Start | Baseline Start | Optional | Enables baseline bars and slip/gain shading
Baseline Finish | Baseline Finish | Optional
Milestone Type | Milestone Type | Optional | Any non-blank value marks a milestone; zero-duration tasks are milestones automatically
Workstream | Category | Optional | Eight values: one color each in the Category Colors card, plus the legend above the chart
Owner | Tooltip Fields | Optional | Shown at the bottom of the tooltip with the field name
Budget ($) | Tooltip Fields | Optional | Numeric; shown with thousands separators
Status | Tooltip Fields | Optional
Duration (days) | (not bound) |  | Convenience column; the visual computes duration from Start and Finish
Finish Variance (days) | (not bound) |  | Finish minus Baseline Finish; positive = late. Can be added to Tooltip Fields

## Notes
BFVZ PowerGantt Lite sample schedule: Project Atlas, ERP implementation (fictional company, synthetic data)
Line items | 100 tasks in 8 phases, 13 milestones, 8 workstreams, 160 dependency links (FS, SS and FF with lags)
Project start | 2026-03-02
Data Date (status date) | 2026-10-16 -- set Schedule card > Data Date to this value. Blank uses today
Baseline finish / current finish | 2027-05-17 / 2027-06-14 -- the program slipped 4 weeks: contract negotiation +14 days, then custom development +21 days on the critical path
Status at the Data Date | 49 complete, 7 in progress, 44 not started
Progress Mode | Hybrid (default): the % Complete field is used where it is above 0; blank or 0 is computed from the Data Date
Date convention | Durations are calendar days; a Finish-to-Start successor starts on the day its predecessor finishes (the convention PowerGantt's critical path engine uses), so the entered dates, the logic, the float and the critical path all agree
Baseline | Baseline dates are the original forward-pass plan; current dates are the same network recomputed with revised durations. Tasks whose dates did not change show no baseline bar (identical baseline)
Schedule Health Check (expected result) | 1 warning, 2 info; the button in the header turns orange
High Float (warning) | ATL-712 Quick reference guides (56 days) and ATL-810 Legacy system decommissioning (49 days): both deliberately tied to a late successor so the check has something to show
High Path Convergence (info) | ATL-506 Interface unit testing and ATL-802 Go/No-Go decision each merge five predecessors
Long Lags (info) | ATL-807 First month-end close: ATL-804FS+25 (the close waits for the first month-end after go-live)
Everything else | No circular logic, no invalid dates, no duplicate or missing IDs, no missing predecessors or successors, no leads, no Start-to-Finish links, no negative float
Critical path | Charter > vendor contract > mobilization > kickoff > finance and supply chain design > conference room pilot > fit-gap > custom development > build complete > mock migration 2 > test environment > SIT 1 and 2 > regression > UAT > UAT exit > test report > Go/No-Go > cutover > go-live > hypercare > closeout
Suggested binding | Phase > Group; Task Name; Task ID; Predecessors; Start; Finish; % Complete (Don't summarize); Baseline Start; Baseline Finish; Milestone Type; Workstream > Category; Owner, Budget ($), Status > Tooltip Fields
Generated | 2026-10-18 by the BFVZ build session (gen_sample.py); regenerate from the script to change the network

## Dependency Legend
Dependency type | Format | Meaning | Example in this schedule
Finish-to-Start | TaskID or TaskIDFS[+lag] | Successor starts when the predecessor finishes (plus lag) | ATL-804FS+25 (ATL-807)
Start-to-Start | TaskIDSS[+lag] | Successor starts when the predecessor starts (plus lag) | ATL-303SS+14 (ATL-304)
Finish-to-Finish | TaskIDFF[+lag] | Successor finishes when the predecessor finishes (plus lag) | ATL-303FF+7 (ATL-310)
Start-to-Finish | TaskIDSF[+lag] | Supported by the visual; not used here (flagged by the Health Check as poor practice)
Multiple | comma-separated | All links must be satisfied; the latest drives the start | ATL-614, ATL-711, ATL-801, ATL-609, ATL-409 (ATL-802)