## Schedule
Project | Phase | Task Name | Task ID | Milestone Type | Predecessors | Start Date | Finish Date | Planned Start | Planned End | Progress % | BL Progress % | Constraint Type | Company | Owner PM | Owner Controller | Contractor PM
Ridgeline Data Hall A | Permitting & Approvals | Permitting — Activity 1 | RLA-0001 |  |  | 2025-03-01 | 2025-03-21 | 2025-03-01 | 2025-03-11 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Permitting & Approvals | Permitting — Activity 2 | RLA-0002 |  | RLA-0001FS | 2025-03-06 | 2025-03-17 | 2025-03-06 | 2025-03-17 | 100 | 97 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Permitting & Approvals | Permitting — Activity 3 | RLA-0003 |  | RLA-0002FS | 2025-03-12 | 2025-03-27 | 2025-03-12 | 2025-03-27 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Permitting & Approvals | Permitting — Activity 4 | RLA-0004 |  | RLA-0003FS | 2025-03-14 | 2025-04-09 | 2025-03-14 | 2025-04-09 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Permitting & Approvals | Permit Milestone — Permitting & Approvals | RLA-0005 | Permit | RLA-0004FS | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Permitting & Approvals | Permit Milestone — Permitting & Approvals | RLA-0006 | Permit | RLA-0005SS+4 | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 1 | RLA-0007 |  | RLA-0006FS | 2025-04-14 | 2025-05-12 | 2025-04-14 | 2025-05-12 | 100 | 100 | SNET | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 2 | RLA-0008 |  | RLA-0007FS | 2025-04-15 | 2025-05-02 | 2025-04-15 | 2025-05-02 | 100 | 98 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 3 | RLA-0009 |  | RLA-0008FS | 2025-04-16 | 2025-05-28 | 2025-04-16 | 2025-05-28 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 4 | RLA-0010 |  | RLA-0009FS | 2025-04-17 | 2025-05-20 | 2025-04-17 | 2025-05-20 | 100 | 98 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 5 | RLA-0011 |  | RLA-0010FS | 2025-04-17 | 2025-05-27 | 2025-04-17 | 2025-05-27 | 100 | 98 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 6 | RLA-0012 |  | RLA-0011FS | 2025-04-18 | 2025-05-28 | 2025-04-18 | 2025-05-28 | 100 | 99 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 7 | RLA-0013 |  | RLA-0012FS | 2025-04-25 | 2025-05-28 | 2025-04-25 | 2025-05-28 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 8 | RLA-0014 |  | RLA-0013FS+2 | 2025-04-28 | 2025-05-28 | 2025-04-28 | 2025-05-28 | 100 | 98 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 9 | RLA-0015 |  | RLA-0014FS | 2025-05-02 | 2025-07-03 | 2025-05-02 | 2025-06-17 | 100 | 97 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 10 | RLA-0016 |  | RLA-0015FS | 2025-05-09 | 2025-05-30 | 2025-05-09 | 2025-05-30 | 100 | 99 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 11 | RLA-0017 |  | RLA-0016FS | 2025-05-14 | 2025-06-18 | 2025-05-14 | 2025-06-06 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 12 | RLA-0018 |  | RLA-0017FS | 2025-05-20 | 2025-07-15 | 2025-05-20 | 2025-07-15 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 13 | RLA-0019 |  | RLA-0018FS | 2025-05-23 | 2025-07-14 | 2025-05-23 | 2025-06-30 | 100 | 97 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 14 | RLA-0020 |  | RLA-0019FS | 2025-05-23 | 2025-07-17 | 2025-05-23 | 2025-07-17 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework — Activity 15 | RLA-0021 |  | RLA-0020FS | 2025-05-29 | 2025-07-02 | 2025-05-29 | 2025-07-02 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Sitework & Civil | Sitework & Civil Complete Milestone | RLA-0022 | Completion | RLA-0021FS | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 1 | RLA-0023 |  | RLA-0022FS | 2025-07-21 | 2025-08-11 | 2025-07-21 | 2025-08-11 | 100 | 97 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 2 | RLA-0024 |  | RLA-0023FS | 2025-07-25 | 2025-08-26 | 2025-07-25 | 2025-08-26 | 100 | 97 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 3 | RLA-0025 |  | RLA-0024FS | 2025-07-31 | 2025-08-18 | 2025-07-31 | 2025-08-18 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 4 | RLA-0026 |  | RLA-0025FS | 2025-08-01 | 2025-09-24 | 2025-08-01 | 2025-09-24 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 5 | RLA-0027 |  | RLA-0026FS | 2025-08-06 | 2025-09-24 | 2025-08-06 | 2025-09-24 | 100 | 97 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 6 | RLA-0028 |  | RLA-0027SS | 2025-08-13 | 2025-09-29 | 2025-08-13 | 2025-09-29 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 7 | RLA-0029 |  | RLA-0028FS | 2025-08-14 | 2025-10-02 | 2025-08-14 | 2025-10-02 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 8 | RLA-0030 |  | RLA-0029FS+2 | 2025-08-14 | 2025-09-03 | 2025-08-14 | 2025-09-03 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 9 | RLA-0031 |  | RLA-0030FS | 2025-08-19 | 2025-09-12 | 2025-08-19 | 2025-09-12 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 10 | RLA-0032 |  | RLA-0031FS | 2025-08-21 | 2025-10-06 | 2025-08-21 | 2025-10-06 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 11 | RLA-0033 |  | RLA-0032FS+7 | 2025-08-22 | 2025-10-16 | 2025-08-22 | 2025-10-16 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations — Activity 12 | RLA-0034 |  | RLA-0033FS | 2025-08-22 | 2025-09-08 | 2025-08-22 | 2025-09-08 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Foundations | Foundations Complete Milestone | RLA-0035 | Completion | RLA-0034FS+8 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 100 | 97 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 1 | RLA-0036 |  | RLA-0035FS | 2025-10-17 | 2025-10-31 | 2025-10-17 | 2025-10-31 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 2 | RLA-0037 |  | RLA-0036FS | 2025-10-21 | 2025-11-28 | 2025-10-21 | 2025-11-28 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 3 | RLA-0038 |  | RLA-0037FS+5 | 2025-10-24 | 2025-12-02 | 2025-10-24 | 2025-12-02 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 4 | RLA-0039 |  | RLA-0038FS | 2025-10-30 | 2025-11-17 | 2025-10-30 | 2025-11-17 | 100 | 98 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 5 | RLA-0040 |  | RLA-0039FS | 2025-10-31 | 2025-12-08 | 2025-10-31 | 2025-12-08 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 6 | RLA-0041 |  | RLA-0040FS | 2025-11-07 | 2025-11-19 | 2025-11-07 | 2025-11-19 | 100 | 98 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 7 | RLA-0042 |  | RLA-0041FS | 2025-11-07 | 2025-11-28 | 2025-11-07 | 2025-11-28 | 100 | 99 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 8 | RLA-0043 |  | RLA-0042SS | 2025-11-13 | 2025-12-17 | 2025-11-13 | 2025-12-17 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 9 | RLA-0044 |  | RLA-0043FS | 2025-11-13 | 2025-11-27 | 2025-11-13 | 2025-11-27 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 10 | RLA-0045 |  | RLA-0044FS | 2025-11-19 | 2026-01-13 | 2025-11-19 | 2026-01-06 | 100 | 98 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 11 | RLA-0046 |  | RLA-0045SS | 2025-11-19 | 2025-12-11 | 2025-11-19 | 2025-12-11 | 100 | 99 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 12 | RLA-0047 |  | RLA-0046FF | 2025-11-26 | 2026-01-13 | 2025-11-26 | 2025-12-24 | 100 | 98 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 13 | RLA-0048 |  | RLA-0047FS | 2025-12-01 | 2026-01-07 | 2025-12-01 | 2025-12-23 | 100 | 99 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 14 | RLA-0049 |  | RLA-0048SS | 2025-12-04 | 2025-12-24 | 2025-12-04 | 2025-12-24 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 15 | RLA-0050 |  | RLA-0049FS | 2025-12-05 | 2026-01-13 | 2025-12-05 | 2026-01-13 | 100 | 97 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel — Activity 16 | RLA-0051 |  | RLA-0050FS | 2025-12-12 | 2026-01-23 | 2025-12-12 | 2026-01-23 | 100 | 97 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Structural Steel | Structural Steel Complete Milestone | RLA-0052 | Completion | RLA-0051FS | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 100 | 97 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 1 | RLA-0053 |  | RLA-0052FS | 2026-01-28 | 2026-03-18 | 2026-01-28 | 2026-03-18 | 80 | 81 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 2 | RLA-0054 |  | RLA-0053FS+8 | 2026-02-03 | 2026-03-19 | 2026-02-03 | 2026-03-19 | 66 | 68 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 3 | RLA-0055 |  | RLA-0054SS | 2026-02-05 | 2026-03-05 | 2026-02-05 | 2026-03-05 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 4 | RLA-0056 |  | RLA-0055FS | 2026-02-11 | 2026-03-20 | 2026-02-11 | 2026-03-20 | 71 | 69 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 5 | RLA-0057 |  | RLA-0056FS | 2026-02-18 | 2026-04-03 | 2026-02-18 | 2026-04-03 | 36 | 33 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 6 | RLA-0058 |  | RLA-0057FS | 2026-02-19 | 2026-03-27 | 2026-02-19 | 2026-03-27 | 55 | 57 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 7 | RLA-0059 |  | RLA-0058FS | 2026-02-24 | 2026-04-21 | 2026-02-24 | 2026-04-21 | 16 | 17 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 8 | RLA-0060 |  | RLA-0059FS | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-16 | 55 | 56 | MSO | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 9 | RLA-0061 |  | RLA-0060FS | 2026-03-02 | 2026-04-22 | 2026-03-02 | 2026-04-22 | 20 | 18 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 10 | RLA-0062 |  | RLA-0061FS | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-03-12 | 57 | 54 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 11 | RLA-0063 |  | RLA-0062FS | 2026-03-02 | 2026-04-02 | 2026-03-02 | 2026-04-02 | 23 | 26 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope — Activity 12 | RLA-0064 |  | RLA-0063FS | 2026-03-05 | 2026-04-30 | 2026-03-05 | 2026-04-30 | 12 | 12 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Building Envelope | Building Envelope Complete Milestone | RLA-0065 | Completion | RLA-0064FS | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 1 | RLA-0066 |  | RLA-0065FS | 2026-05-05 | 2026-06-05 | 2026-05-05 | 2026-06-05 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 2 | RLA-0067 |  | RLA-0066SS+3 | 2026-05-07 | 2026-06-09 | 2026-05-07 | 2026-06-09 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 3 | RLA-0068 |  | RLA-0067FS | 2026-05-14 | 2026-06-08 | 2026-05-14 | 2026-06-08 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 4 | RLA-0069 |  | RLA-0068FS | 2026-05-19 | 2026-06-17 | 2026-05-19 | 2026-06-17 | 0 | 0 | MSO | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 5 | RLA-0070 |  | RLA-0069FS | 2026-05-21 | 2026-06-02 | 2026-05-21 | 2026-06-02 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 6 | RLA-0071 |  | RLA-0070FS+4 | 2026-05-26 | 2026-06-25 | 2026-05-26 | 2026-06-25 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 7 | RLA-0072 |  | RLA-0071FF | 2026-05-29 | 2026-06-24 | 2026-05-29 | 2026-06-24 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 8 | RLA-0073 |  | RLA-0072FS | 2026-05-29 | 2026-06-11 | 2026-05-29 | 2026-06-11 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 9 | RLA-0074 |  | RLA-0073FS | 2026-06-01 | 2026-07-09 | 2026-06-01 | 2026-07-09 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 10 | RLA-0075 |  | RLA-0074FS+4 | 2026-06-01 | 2026-07-03 | 2026-06-01 | 2026-07-03 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 11 | RLA-0076 |  | RLA-0075FS+3 | 2026-06-01 | 2026-06-15 | 2026-06-01 | 2026-06-15 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 12 | RLA-0077 |  | RLA-0076FS | 2026-06-05 | 2026-06-26 | 2026-06-05 | 2026-06-26 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 13 | RLA-0078 |  | RLA-0077FS+4 | 2026-06-08 | 2026-06-29 | 2026-06-08 | 2026-06-29 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 14 | RLA-0079 |  | RLA-0078FS | 2026-06-15 | 2026-07-30 | 2026-06-15 | 2026-07-30 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 15 | RLA-0080 |  | RLA-0079FS | 2026-06-22 | 2026-07-29 | 2026-06-22 | 2026-07-29 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 16 | RLA-0081 |  | RLA-0080FS | 2026-06-29 | 2026-08-17 | 2026-06-29 | 2026-08-17 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 17 | RLA-0082 |  | RLA-0081FS | 2026-07-02 | 2026-07-22 | 2026-07-02 | 2026-07-22 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 18 | RLA-0083 |  | RLA-0082FS | 2026-07-09 | 2026-08-05 | 2026-07-09 | 2026-08-05 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 19 | RLA-0084 |  | RLA-0083FS | 2026-07-14 | 2026-09-03 | 2026-07-14 | 2026-09-03 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 20 | RLA-0085 |  | RLA-0084FS | 2026-07-17 | 2026-08-21 | 2026-07-17 | 2026-08-21 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 21 | RLA-0086 |  | RLA-0085FS | 2026-07-21 | 2026-09-14 | 2026-07-21 | 2026-09-14 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In — Activity 22 | RLA-0087 |  | RLA-0086FS | 2026-07-27 | 2026-09-08 | 2026-07-27 | 2026-08-31 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | MEP Rough-In | MEP Rough-In Complete Milestone | RLA-0088 | Completion | RLA-0087FS | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 1 | RLA-0089 |  | RLA-0088FS | 2026-09-16 | 2026-10-16 | 2026-09-16 | 2026-10-16 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 2 | RLA-0090 |  | RLA-0089FS | 2026-09-21 | 2026-11-03 | 2026-09-21 | 2026-11-03 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 3 | RLA-0091 |  | RLA-0090FS | 2026-09-23 | 2026-11-13 | 2026-09-23 | 2026-11-13 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 4 | RLA-0092 |  | RLA-0091FS | 2026-09-24 | 2026-10-21 | 2026-09-24 | 2026-10-21 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 5 | RLA-0093 |  | RLA-0092FS | 2026-09-24 | 2026-10-30 | 2026-09-24 | 2026-10-30 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 6 | RLA-0094 |  | RLA-0093FS | 2026-09-28 | 2026-10-23 | 2026-09-28 | 2026-10-16 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 7 | RLA-0095 |  | RLA-0094FS | 2026-09-28 | 2026-10-16 | 2026-09-28 | 2026-10-16 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 8 | RLA-0096 |  | RLA-0095FS | 2026-10-01 | 2026-11-10 | 2026-10-01 | 2026-10-30 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 9 | RLA-0097 |  | RLA-0096FS | 2026-10-07 | 2026-10-30 | 2026-10-07 | 2026-10-30 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 10 | RLA-0098 |  | RLA-0097SS | 2026-10-13 | 2026-11-12 | 2026-10-13 | 2026-11-12 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 11 | RLA-0099 |  | RLA-0098FS | 2026-10-19 | 2026-11-25 | 2026-10-19 | 2026-11-25 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 12 | RLA-0100 |  | RLA-0099FS | 2026-10-21 | 2026-11-19 | 2026-10-21 | 2026-11-19 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 13 | RLA-0101 |  | RLA-0100FS+4 | 2026-10-26 | 2026-12-11 | 2026-10-26 | 2026-12-11 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 14 | RLA-0102 |  | RLA-0101SS | 2026-10-26 | 2026-12-16 | 2026-10-26 | 2026-12-16 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out — Activity 15 | RLA-0103 |  | RLA-0102SS | 2026-10-29 | 2026-12-04 | 2026-10-29 | 2026-11-25 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Electrical Fit-Out | Electrical Fit-Out Complete Milestone | RLA-0104 | Completion | RLA-0103FS | 2026-12-04 | 2026-12-04 | 2026-12-04 | 2026-12-04 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 1 | RLA-0105 |  | RLA-0104FS | 2026-12-17 | 2027-02-08 | 2026-12-17 | 2027-02-08 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 2 | RLA-0106 |  | RLA-0105FS+5 | 2026-12-23 | 2027-02-17 | 2026-12-23 | 2027-02-17 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 3 | RLA-0107 |  | RLA-0106FF | 2026-12-23 | 2027-02-11 | 2026-12-23 | 2027-01-26 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 4 | RLA-0108 |  | RLA-0107FS | 2026-12-28 | 2027-01-22 | 2026-12-28 | 2027-01-22 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 5 | RLA-0109 |  | RLA-0108FS | 2026-12-28 | 2027-02-19 | 2026-12-28 | 2027-02-19 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 6 | RLA-0110 |  | RLA-0109FS | 2026-12-31 | 2027-02-10 | 2026-12-31 | 2027-02-10 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Fire Protection — Activity 7 | RLA-0111 |  | RLA-0110FS | 2027-01-05 | 2027-01-28 | 2027-01-05 | 2027-01-15 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | RLA-0112 | Inspection | RLA-0111FS | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | RLA-0113 | Inspection | RLA-0112FS | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 1 | RLA-0114 |  | RLA-0113FS | 2027-02-24 | 2027-03-18 | 2027-02-24 | 2027-03-18 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 2 | RLA-0115 |  | RLA-0114FS | 2027-02-24 | 2027-05-06 | 2027-02-24 | 2027-04-19 | 0 | 0 | MSO | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 3 | RLA-0116 |  | RLA-0115FS | 2027-02-24 | 2027-03-26 | 2027-02-24 | 2027-03-26 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 4 | RLA-0117 |  | RLA-0116FS | 2027-03-02 | 2027-04-07 | 2027-03-02 | 2027-04-07 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 5 | RLA-0118 |  | RLA-0117FS | 2027-03-05 | 2027-03-30 | 2027-03-05 | 2027-03-30 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 6 | RLA-0119 |  | RLA-0118FS | 2027-03-10 | 2027-04-14 | 2027-03-10 | 2027-04-14 | 0 | 0 | SNET | ColdStream Mechanical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 7 | RLA-0120 |  | RLA-0119FS | 2027-03-11 | 2027-05-05 | 2027-03-11 | 2027-05-05 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Testing — Activity 8 | RLA-0121 |  | RLA-0120FF | 2027-03-15 | 2027-05-05 | 2027-03-15 | 2027-05-05 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | RLA-0122 | Inspection | RLA-0121FS | 2027-05-05 | 2027-05-05 | 2027-05-05 | 2027-05-05 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | RLA-0123 | Inspection | RLA-0122FS | 2027-05-05 | 2027-05-05 | 2027-05-05 | 2027-05-05 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist — Activity 1 | RLA-0124 |  | RLA-0123FS | 2027-05-07 | 2027-05-24 | 2027-05-07 | 2027-05-24 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist — Activity 2 | RLA-0125 |  | RLA-0124FS | 2027-05-07 | 2027-05-21 | 2027-05-07 | 2027-05-21 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist — Activity 3 | RLA-0126 |  | RLA-0125FF | 2027-05-07 | 2027-05-14 | 2027-05-07 | 2027-05-14 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist — Activity 4 | RLA-0127 |  | RLA-0126SS | 2027-05-10 | 2027-05-14 | 2027-05-10 | 2027-05-14 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist — Activity 5 | RLA-0128 |  | RLA-0127FS+7 | 2027-05-11 | 2027-06-01 | 2027-05-11 | 2027-06-01 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Inspection Milestone — Punchlist & Turnover | RLA-0129 | Inspection | RLA-0128FS | 2027-06-01 | 2027-06-01 | 2027-06-01 | 2027-06-01 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Data Hall A | Punchlist & Turnover | Punchlist & Turnover Complete Milestone | RLA-0130 | Completion | RLA-0129FS | 2027-06-01 | 2027-06-01 | 2027-06-01 | 2027-06-01 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Mike Rodriguez
Ridgeline Central Plant | Permitting & Approvals | Permitting — Activity 1 | RLC-0001 |  |  | 2025-06-01 | 2025-06-20 | 2025-06-01 | 2025-06-20 | 100 | 99 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Permitting & Approvals | Permit Milestone — Permitting & Approvals | RLC-0002 | Permit | RLC-0001FS | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 100 | 98 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Permitting & Approvals | Permit Milestone — Permitting & Approvals | RLC-0003 | Permit | RLC-0002SS | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 1 | RLC-0004 |  | RLC-0003FS | 2025-06-23 | 2025-08-13 | 2025-06-23 | 2025-08-13 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 2 | RLC-0005 |  | RLC-0004FS | 2025-06-25 | 2025-08-15 | 2025-06-25 | 2025-08-15 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 3 | RLC-0006 |  | RLC-0005FS | 2025-07-02 | 2025-08-20 | 2025-07-02 | 2025-08-20 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 4 | RLC-0007 |  | RLC-0006FS | 2025-07-07 | 2025-08-07 | 2025-07-07 | 2025-08-07 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 5 | RLC-0008 |  | RLC-0007FS | 2025-07-09 | 2025-08-28 | 2025-07-09 | 2025-08-20 | 100 | 98 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework — Activity 6 | RLC-0009 |  | RLC-0008FS | 2025-07-10 | 2025-08-21 | 2025-07-10 | 2025-08-21 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Sitework & Civil | Sitework & Civil Complete Milestone | RLC-0010 | Completion | RLC-0009FS | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 100 | 99 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations — Activity 1 | RLC-0011 |  | RLC-0010FS | 2025-08-29 | 2025-10-13 | 2025-08-29 | 2025-10-13 | 100 | 99 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations — Activity 2 | RLC-0012 |  | RLC-0011FS | 2025-09-01 | 2025-10-17 | 2025-09-01 | 2025-10-17 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations — Activity 3 | RLC-0013 |  | RLC-0012SS | 2025-09-03 | 2025-09-29 | 2025-09-03 | 2025-09-29 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations — Activity 4 | RLC-0014 |  | RLC-0013FS | 2025-09-08 | 2025-09-29 | 2025-09-08 | 2025-09-29 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations — Activity 5 | RLC-0015 |  | RLC-0014FS+6 | 2025-09-12 | 2025-10-29 | 2025-09-12 | 2025-10-29 | 100 | 99 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Foundations | Foundations Complete Milestone | RLC-0016 | Completion | RLC-0015FS | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | 100 | 99 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 1 | RLC-0017 |  | RLC-0016FS | 2025-11-03 | 2025-12-03 | 2025-11-03 | 2025-12-03 | 100 | 100 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 2 | RLC-0018 |  | RLC-0017FS | 2025-11-10 | 2025-12-24 | 2025-11-10 | 2025-12-08 | 100 | 99 | SNET | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 3 | RLC-0019 |  | RLC-0018FS | 2025-11-10 | 2025-12-01 | 2025-11-10 | 2025-12-01 | 100 | 100 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 4 | RLC-0020 |  | RLC-0019FS | 2025-11-14 | 2026-01-01 | 2025-11-14 | 2026-01-01 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 5 | RLC-0021 |  | RLC-0020FS | 2025-11-18 | 2026-01-15 | 2025-11-18 | 2026-01-02 | 100 | 97 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 6 | RLC-0022 |  | RLC-0021FS+4 | 2025-11-24 | 2026-01-06 | 2025-11-24 | 2026-01-06 | 100 | 97 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel — Activity 7 | RLC-0023 |  | RLC-0022FS | 2025-12-01 | 2025-12-18 | 2025-12-01 | 2025-12-18 | 100 | 99 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Structural Steel | Structural Steel Complete Milestone | RLC-0024 | Completion | RLC-0023FS | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope — Activity 1 | RLC-0025 |  | RLC-0024FS | 2026-01-20 | 2026-02-18 | 2026-01-20 | 2026-02-18 | 100 | 100 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope — Activity 2 | RLC-0026 |  | RLC-0025FS | 2026-01-22 | 2026-02-03 | 2026-01-22 | 2026-02-03 | 100 | 98 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope — Activity 3 | RLC-0027 |  | RLC-0026FS | 2026-01-23 | 2026-02-13 | 2026-01-23 | 2026-02-03 | 100 | 100 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope — Activity 4 | RLC-0028 |  | RLC-0027FS | 2026-01-30 | 2026-03-06 | 2026-01-30 | 2026-02-18 | 100 | 100 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope — Activity 5 | RLC-0029 |  | RLC-0028FS | 2026-02-04 | 2026-03-13 | 2026-02-04 | 2026-03-13 | 76 | 78 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Building Envelope | Building Envelope Complete Milestone | RLC-0030 | Completion | RLC-0029SS+2 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 1 | RLC-0031 |  | RLC-0030FS | 2026-03-16 | 2026-04-07 | 2026-03-16 | 2026-04-07 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 2 | RLC-0032 |  | RLC-0031FS | 2026-03-19 | 2026-04-28 | 2026-03-19 | 2026-04-28 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 3 | RLC-0033 |  | RLC-0032FS | 2026-03-26 | 2026-04-16 | 2026-03-26 | 2026-04-16 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 4 | RLC-0034 |  | RLC-0033FS | 2026-03-31 | 2026-04-30 | 2026-03-31 | 2026-04-30 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 5 | RLC-0035 |  | RLC-0034FF | 2026-04-07 | 2026-05-15 | 2026-04-07 | 2026-05-15 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 6 | RLC-0036 |  | RLC-0035FS | 2026-04-07 | 2026-04-24 | 2026-04-07 | 2026-04-24 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 7 | RLC-0037 |  | RLC-0036SS | 2026-04-14 | 2026-06-04 | 2026-04-14 | 2026-05-20 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 8 | RLC-0038 |  | RLC-0037FS | 2026-04-16 | 2026-06-09 | 2026-04-16 | 2026-05-22 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 9 | RLC-0039 |  | RLC-0038FS | 2026-04-16 | 2026-05-29 | 2026-04-16 | 2026-05-29 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In — Activity 10 | RLC-0040 |  | RLC-0039FS | 2026-04-22 | 2026-05-05 | 2026-04-22 | 2026-05-05 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | MEP Rough-In | MEP Rough-In Complete Milestone | RLC-0041 | Completion | RLC-0040SS | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 1 | RLC-0042 |  | RLC-0041FS | 2026-06-12 | 2026-08-03 | 2026-06-12 | 2026-07-29 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 2 | RLC-0043 |  | RLC-0042FS | 2026-06-17 | 2026-07-31 | 2026-06-17 | 2026-07-31 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 3 | RLC-0044 |  | RLC-0043FS+2 | 2026-06-17 | 2026-07-06 | 2026-06-17 | 2026-07-06 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 4 | RLC-0045 |  | RLC-0044FS | 2026-06-22 | 2026-08-10 | 2026-06-22 | 2026-08-10 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 5 | RLC-0046 |  | RLC-0045FS | 2026-06-22 | 2026-08-10 | 2026-06-22 | 2026-08-10 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out — Activity 6 | RLC-0047 |  | RLC-0046FS | 2026-06-25 | 2026-07-27 | 2026-06-25 | 2026-07-27 | 0 | 0 |  | DeepCore Foundations | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Electrical Fit-Out | Electrical Fit-Out Complete Milestone | RLC-0048 | Completion | RLC-0047FS | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Fire Protection & Life Safety | Fire Protection — Activity 1 | RLC-0049 |  | RLC-0048FS | 2026-08-11 | 2026-09-02 | 2026-08-11 | 2026-09-02 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Fire Protection & Life Safety | Fire Protection — Activity 2 | RLC-0050 |  | RLC-0049FS | 2026-08-11 | 2026-09-22 | 2026-08-11 | 2026-09-22 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | RLC-0051 | Inspection | RLC-0050FS | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-22 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | RLC-0052 | Inspection | RLC-0051FS | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-22 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Testing & Commissioning | Testing — Activity 1 | RLC-0053 |  | RLC-0052FS | 2026-09-24 | 2026-11-12 | 2026-09-24 | 2026-11-05 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Testing & Commissioning | Testing — Activity 2 | RLC-0054 |  | RLC-0053FS | 2026-09-29 | 2026-10-16 | 2026-09-29 | 2026-10-16 | 0 | 0 |  | TerraForm Earthworks | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Testing & Commissioning | Testing — Activity 3 | RLC-0055 |  | RLC-0054SS | 2026-10-06 | 2026-12-16 | 2026-10-06 | 2026-11-30 | 0 | 0 |  | AquaGuard Fire & Plumbing | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | RLC-0056 | Inspection | RLC-0055FS | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | RLC-0057 | Inspection | RLC-0056FS+8 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 0 | 0 |  | Brightfield Electrical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Punchlist & Turnover | Punchlist — Activity 1 | RLC-0058 |  | RLC-0057FS | 2026-12-21 | 2027-01-11 | 2026-12-21 | 2027-01-11 | 0 | 0 |  | ColdStream Mechanical | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Punchlist & Turnover | Inspection Milestone — Punchlist & Turnover | RLC-0059 | Inspection | RLC-0058FF | 2027-01-11 | 2027-01-11 | 2027-01-11 | 2027-01-11 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ridgeline Central Plant | Punchlist & Turnover | Punchlist & Turnover Complete Milestone | RLC-0060 | Completion | RLC-0059FS | 2027-01-11 | 2027-01-11 | 2027-01-11 | 2027-01-11 | 0 | 0 |  | SteelRise Erectors | Sarah Mitchell | David Chen | Karen Osei
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 1 | IW1-0001 |  |  | 2025-04-01 | 2025-04-09 | 2025-04-01 | 2025-04-09 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 2 | IW1-0002 |  | IW1-0001FS | 2025-04-01 | 2025-04-09 | 2025-04-01 | 2025-04-09 | 100 | 97 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 3 | IW1-0003 |  | IW1-0002FF | 2025-04-04 | 2025-04-29 | 2025-04-04 | 2025-04-29 | 100 | 99 | SNET | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 4 | IW1-0004 |  | IW1-0003FS | 2025-04-10 | 2025-05-08 | 2025-04-10 | 2025-05-08 | 100 | 99 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 5 | IW1-0005 |  | IW1-0004FS | 2025-04-16 | 2025-04-25 | 2025-04-16 | 2025-04-25 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 6 | IW1-0006 |  | IW1-0005FS | 2025-04-18 | 2025-05-02 | 2025-04-18 | 2025-05-02 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permitting — Activity 7 | IW1-0007 |  | IW1-0006FS | 2025-04-18 | 2025-05-09 | 2025-04-18 | 2025-05-09 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permit Milestone — Permitting & Approvals | IW1-0008 | Permit | IW1-0007FS | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Permitting & Approvals | Permit Milestone — Permitting & Approvals | IW1-0009 | Permit | IW1-0008FS | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 100 | 98 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 1 | IW1-0010 |  | IW1-0009FS | 2025-05-14 | 2025-06-02 | 2025-05-14 | 2025-06-02 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 2 | IW1-0011 |  | IW1-0010SS | 2025-05-21 | 2025-06-12 | 2025-05-21 | 2025-06-12 | 100 | 97 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 3 | IW1-0012 |  | IW1-0011FS | 2025-05-27 | 2025-07-15 | 2025-05-27 | 2025-07-15 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 4 | IW1-0013 |  | IW1-0012FS | 2025-05-28 | 2025-06-25 | 2025-05-28 | 2025-06-25 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 5 | IW1-0014 |  | IW1-0013FS | 2025-06-04 | 2025-06-18 | 2025-06-04 | 2025-06-18 | 100 | 98 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 6 | IW1-0015 |  | IW1-0014FS | 2025-06-11 | 2025-07-07 | 2025-06-11 | 2025-07-07 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 7 | IW1-0016 |  | IW1-0015FS | 2025-06-18 | 2025-07-24 | 2025-06-18 | 2025-07-24 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 8 | IW1-0017 |  | IW1-0016FS | 2025-06-20 | 2025-07-18 | 2025-06-20 | 2025-07-18 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 9 | IW1-0018 |  | IW1-0017FS | 2025-06-26 | 2025-08-21 | 2025-06-26 | 2025-08-21 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 10 | IW1-0019 |  | IW1-0018FS | 2025-07-03 | 2025-07-18 | 2025-07-03 | 2025-07-18 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 11 | IW1-0020 |  | IW1-0019FS | 2025-07-03 | 2025-08-08 | 2025-07-03 | 2025-08-08 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 12 | IW1-0021 |  | IW1-0020SS | 2025-07-08 | 2025-08-07 | 2025-07-08 | 2025-08-07 | 100 | 99 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 13 | IW1-0022 |  | IW1-0021FS | 2025-07-08 | 2025-08-21 | 2025-07-08 | 2025-08-21 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 14 | IW1-0023 |  | IW1-0022FS | 2025-07-09 | 2025-08-15 | 2025-07-09 | 2025-07-31 | 100 | 97 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 15 | IW1-0024 |  | IW1-0023FS | 2025-07-10 | 2025-08-13 | 2025-07-10 | 2025-08-13 | 100 | 97 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 16 | IW1-0025 |  | IW1-0024FS | 2025-07-14 | 2025-08-22 | 2025-07-14 | 2025-08-11 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 17 | IW1-0026 |  | IW1-0025FS | 2025-07-21 | 2025-08-01 | 2025-07-21 | 2025-08-01 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 18 | IW1-0027 |  | IW1-0026FS+4 | 2025-07-25 | 2025-08-27 | 2025-07-25 | 2025-08-27 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 19 | IW1-0028 |  | IW1-0027FS | 2025-07-31 | 2025-09-25 | 2025-07-31 | 2025-09-25 | 100 | 99 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 20 | IW1-0029 |  | IW1-0028FS | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-15 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework — Activity 21 | IW1-0030 |  | IW1-0029FS | 2025-08-05 | 2025-09-30 | 2025-08-05 | 2025-09-11 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Sitework & Civil | Sitework & Civil Complete Milestone | IW1-0031 | Completion | IW1-0030FS | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 1 | IW1-0032 |  | IW1-0031FS | 2025-10-02 | 2025-11-07 | 2025-10-02 | 2025-10-30 | 100 | 99 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 2 | IW1-0033 |  | IW1-0032FS | 2025-10-08 | 2025-11-24 | 2025-10-08 | 2025-11-24 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 3 | IW1-0034 |  | IW1-0033SS | 2025-10-10 | 2025-12-02 | 2025-10-10 | 2025-11-17 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 4 | IW1-0035 |  | IW1-0034FS | 2025-10-15 | 2025-11-11 | 2025-10-15 | 2025-11-11 | 100 | 97 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 5 | IW1-0036 |  | IW1-0035FF | 2025-10-15 | 2025-12-03 | 2025-10-15 | 2025-12-03 | 100 | 97 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 6 | IW1-0037 |  | IW1-0036FS | 2025-10-22 | 2025-12-01 | 2025-10-22 | 2025-12-01 | 100 | 100 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 7 | IW1-0038 |  | IW1-0037SS | 2025-10-22 | 2025-12-11 | 2025-10-22 | 2025-12-11 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 8 | IW1-0039 |  | IW1-0038FS | 2025-10-29 | 2025-11-14 | 2025-10-29 | 2025-11-14 | 100 | 97 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 9 | IW1-0040 |  | IW1-0039FS | 2025-10-29 | 2025-12-26 | 2025-10-29 | 2025-12-16 | 100 | 100 | SNET | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 10 | IW1-0041 |  | IW1-0040FS | 2025-10-31 | 2025-12-15 | 2025-10-31 | 2025-12-15 | 100 | 99 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 11 | IW1-0042 |  | IW1-0041FS | 2025-11-03 | 2025-12-08 | 2025-11-03 | 2025-12-08 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 12 | IW1-0043 |  | IW1-0042FS | 2025-11-05 | 2025-12-09 | 2025-11-05 | 2025-12-09 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 13 | IW1-0044 |  | IW1-0043FS | 2025-11-06 | 2025-11-27 | 2025-11-06 | 2025-11-27 | 100 | 97 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 14 | IW1-0045 |  | IW1-0044FS | 2025-11-13 | 2025-12-23 | 2025-11-13 | 2025-12-23 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 15 | IW1-0046 |  | IW1-0045FS | 2025-11-17 | 2025-12-12 | 2025-11-17 | 2025-12-12 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 16 | IW1-0047 |  | IW1-0046FS | 2025-11-19 | 2025-12-02 | 2025-11-19 | 2025-12-02 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations — Activity 17 | IW1-0048 |  | IW1-0047FS | 2025-11-21 | 2025-12-09 | 2025-11-21 | 2025-12-09 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Foundations | Foundations Complete Milestone | IW1-0049 | Completion | IW1-0048FF | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 1 | IW1-0050 |  | IW1-0049FS | 2025-12-30 | 2026-01-21 | 2025-12-30 | 2026-01-21 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 2 | IW1-0051 |  | IW1-0050SS+2 | 2025-12-31 | 2026-01-27 | 2025-12-31 | 2026-01-27 | 100 | 99 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 3 | IW1-0052 |  | IW1-0051FS | 2026-01-02 | 2026-01-28 | 2026-01-02 | 2026-01-28 | 100 | 99 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 4 | IW1-0053 |  | IW1-0052FS | 2026-01-05 | 2026-02-06 | 2026-01-05 | 2026-02-06 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 5 | IW1-0054 |  | IW1-0053FS | 2026-01-12 | 2026-03-09 | 2026-01-12 | 2026-03-09 | 95 | 96 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 6 | IW1-0055 |  | IW1-0054FS | 2026-01-12 | 2026-02-11 | 2026-01-12 | 2026-01-22 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 7 | IW1-0056 |  | IW1-0055FF | 2026-01-19 | 2026-03-13 | 2026-01-19 | 2026-03-13 | 95 | 97 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 8 | IW1-0057 |  | IW1-0056FS | 2026-01-22 | 2026-03-05 | 2026-01-22 | 2026-02-27 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 9 | IW1-0058 |  | IW1-0057FF | 2026-01-29 | 2026-03-10 | 2026-01-29 | 2026-03-10 | 95 | 96 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 10 | IW1-0059 |  | IW1-0058FS | 2026-01-30 | 2026-03-11 | 2026-01-30 | 2026-03-11 | 90 | 90 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 11 | IW1-0060 |  | IW1-0059FS | 2026-02-02 | 2026-03-20 | 2026-02-02 | 2026-03-20 | 69 | 67 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 12 | IW1-0061 |  | IW1-0060FS+5 | 2026-02-06 | 2026-04-02 | 2026-02-06 | 2026-04-02 | 54 | 52 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 13 | IW1-0062 |  | IW1-0061FS | 2026-02-06 | 2026-04-03 | 2026-02-06 | 2026-03-17 | 53 | 52 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 14 | IW1-0063 |  | IW1-0062FS | 2026-02-11 | 2026-03-26 | 2026-02-11 | 2026-03-26 | 60 | 59 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 15 | IW1-0064 |  | IW1-0063FS | 2026-02-17 | 2026-04-02 | 2026-02-17 | 2026-04-02 | 50 | 47 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 16 | IW1-0065 |  | IW1-0064FS | 2026-02-20 | 2026-03-12 | 2026-02-20 | 2026-03-12 | 80 | 81 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 17 | IW1-0066 |  | IW1-0065FS | 2026-02-26 | 2026-04-17 | 2026-02-26 | 2026-04-13 | 20 | 21 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 18 | IW1-0067 |  | IW1-0066FF | 2026-03-04 | 2026-04-13 | 2026-03-04 | 2026-04-13 | 12 | 11 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 19 | IW1-0068 |  | IW1-0067FS | 2026-03-10 | 2026-05-05 | 2026-03-10 | 2026-05-05 | 0 | 0 | SNET | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 20 | IW1-0069 |  | IW1-0068FS | 2026-03-13 | 2026-04-03 | 2026-03-13 | 2026-04-03 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 21 | IW1-0070 |  | IW1-0069FS | 2026-03-17 | 2026-05-08 | 2026-03-17 | 2026-05-08 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel — Activity 22 | IW1-0071 |  | IW1-0070FS | 2026-03-23 | 2026-04-07 | 2026-03-23 | 2026-04-07 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Structural Steel | Structural Steel Complete Milestone | IW1-0072 | Completion | IW1-0071FS+7 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 1 | IW1-0073 |  | IW1-0072FS | 2026-05-12 | 2026-06-19 | 2026-05-12 | 2026-06-19 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 2 | IW1-0074 |  | IW1-0073SS | 2026-05-18 | 2026-07-03 | 2026-05-18 | 2026-07-03 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 3 | IW1-0075 |  | IW1-0074FS | 2026-05-22 | 2026-06-15 | 2026-05-22 | 2026-06-15 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 4 | IW1-0076 |  | IW1-0075FS | 2026-05-27 | 2026-06-23 | 2026-05-27 | 2026-06-23 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 5 | IW1-0077 |  | IW1-0076FF | 2026-06-02 | 2026-07-06 | 2026-06-02 | 2026-07-06 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 6 | IW1-0078 |  | IW1-0077FS | 2026-06-09 | 2026-07-15 | 2026-06-09 | 2026-07-15 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 7 | IW1-0079 |  | IW1-0078SS | 2026-06-11 | 2026-07-31 | 2026-06-11 | 2026-07-13 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 8 | IW1-0080 |  | IW1-0079FS | 2026-06-11 | 2026-07-17 | 2026-06-11 | 2026-07-17 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 9 | IW1-0081 |  | IW1-0080FS | 2026-06-12 | 2026-08-05 | 2026-06-12 | 2026-08-05 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 10 | IW1-0082 |  | IW1-0081FS+6 | 2026-06-18 | 2026-07-08 | 2026-06-18 | 2026-07-08 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 11 | IW1-0083 |  | IW1-0082FS | 2026-06-18 | 2026-07-03 | 2026-06-18 | 2026-07-03 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 12 | IW1-0084 |  | IW1-0083SS | 2026-06-23 | 2026-07-17 | 2026-06-23 | 2026-07-17 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 13 | IW1-0085 |  | IW1-0084SS+6 | 2026-06-25 | 2026-08-04 | 2026-06-25 | 2026-08-04 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 14 | IW1-0086 |  | IW1-0085FS | 2026-06-26 | 2026-07-10 | 2026-06-26 | 2026-07-10 | 0 | 0 | MSO | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 15 | IW1-0087 |  | IW1-0086SS | 2026-07-03 | 2026-07-30 | 2026-07-03 | 2026-07-30 | 0 | 0 | SNET | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 16 | IW1-0088 |  | IW1-0087FS | 2026-07-08 | 2026-08-13 | 2026-07-08 | 2026-08-13 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope — Activity 17 | IW1-0089 |  | IW1-0088FS | 2026-07-10 | 2026-09-01 | 2026-07-10 | 2026-09-01 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Building Envelope | Building Envelope Complete Milestone | IW1-0090 | Completion | IW1-0089FS | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 1 | IW1-0091 |  | IW1-0090FS | 2026-09-02 | 2026-09-29 | 2026-09-02 | 2026-09-29 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 2 | IW1-0092 |  | IW1-0091FS+3 | 2026-09-08 | 2026-10-27 | 2026-09-08 | 2026-10-27 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 3 | IW1-0093 |  | IW1-0092FS | 2026-09-10 | 2026-09-22 | 2026-09-10 | 2026-09-22 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 4 | IW1-0094 |  | IW1-0093FS+2 | 2026-09-14 | 2026-09-24 | 2026-09-14 | 2026-09-24 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 5 | IW1-0095 |  | IW1-0094SS | 2026-09-21 | 2026-11-05 | 2026-09-21 | 2026-11-05 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 6 | IW1-0096 |  | IW1-0095FS | 2026-09-23 | 2026-10-29 | 2026-09-23 | 2026-10-29 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 7 | IW1-0097 |  | IW1-0096SS | 2026-09-28 | 2026-11-10 | 2026-09-28 | 2026-11-10 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 8 | IW1-0098 |  | IW1-0097SS+5 | 2026-10-05 | 2026-11-05 | 2026-10-05 | 2026-11-05 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 9 | IW1-0099 |  | IW1-0098FS | 2026-10-09 | 2026-11-11 | 2026-10-09 | 2026-10-26 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 10 | IW1-0100 |  | IW1-0099FS | 2026-10-09 | 2026-11-30 | 2026-10-09 | 2026-11-30 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 11 | IW1-0101 |  | IW1-0100FS | 2026-10-14 | 2026-11-11 | 2026-10-14 | 2026-10-26 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 12 | IW1-0102 |  | IW1-0101FS | 2026-10-19 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 13 | IW1-0103 |  | IW1-0102FF | 2026-10-26 | 2026-12-10 | 2026-10-26 | 2026-12-07 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 14 | IW1-0104 |  | IW1-0103FS | 2026-11-02 | 2026-11-24 | 2026-11-02 | 2026-11-24 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 15 | IW1-0105 |  | IW1-0104FS | 2026-11-05 | 2026-12-25 | 2026-11-05 | 2026-12-25 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 16 | IW1-0106 |  | IW1-0105FS | 2026-11-05 | 2026-12-17 | 2026-11-05 | 2026-12-17 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 17 | IW1-0107 |  | IW1-0106FS | 2026-11-05 | 2026-11-17 | 2026-11-05 | 2026-11-17 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 18 | IW1-0108 |  | IW1-0107FS | 2026-11-06 | 2026-12-08 | 2026-11-06 | 2026-12-08 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 19 | IW1-0109 |  | IW1-0108FS | 2026-11-13 | 2026-11-27 | 2026-11-13 | 2026-11-27 | 0 | 0 | SNET | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 20 | IW1-0110 |  | IW1-0109FS+5 | 2026-11-19 | 2026-12-25 | 2026-11-19 | 2026-12-09 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 21 | IW1-0111 |  | IW1-0110FS | 2026-11-20 | 2026-12-07 | 2026-11-20 | 2026-12-07 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 22 | IW1-0112 |  | IW1-0111FS | 2026-11-23 | 2026-12-31 | 2026-11-23 | 2026-12-31 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 23 | IW1-0113 |  | IW1-0112FS | 2026-11-23 | 2026-12-28 | 2026-11-23 | 2026-12-28 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 24 | IW1-0114 |  | IW1-0113FF | 2026-11-27 | 2027-01-15 | 2026-11-27 | 2027-01-15 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 25 | IW1-0115 |  | IW1-0114FS | 2026-12-04 | 2027-01-13 | 2026-12-04 | 2027-01-13 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 26 | IW1-0116 |  | IW1-0115FS | 2026-12-07 | 2027-01-07 | 2026-12-07 | 2027-01-07 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 27 | IW1-0117 |  | IW1-0116FS | 2026-12-10 | 2027-01-27 | 2026-12-10 | 2027-01-27 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 28 | IW1-0118 |  | IW1-0117FS | 2026-12-15 | 2027-01-01 | 2026-12-15 | 2027-01-01 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 29 | IW1-0119 |  | IW1-0118FS+8 | 2026-12-22 | 2027-02-04 | 2026-12-22 | 2027-02-04 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 30 | IW1-0120 |  | IW1-0119SS | 2026-12-25 | 2027-01-25 | 2026-12-25 | 2027-01-25 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In — Activity 31 | IW1-0121 |  | IW1-0120FS | 2027-01-01 | 2027-02-12 | 2027-01-01 | 2027-01-28 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | MEP Rough-In | MEP Rough-In Complete Milestone | IW1-0122 | Completion | IW1-0121FS | 2027-02-12 | 2027-02-12 | 2027-02-12 | 2027-02-12 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 1 | IW1-0123 |  | IW1-0122FS | 2027-02-16 | 2027-03-22 | 2027-02-16 | 2027-03-22 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 2 | IW1-0124 |  | IW1-0123FS | 2027-02-23 | 2027-03-15 | 2027-02-23 | 2027-03-15 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 3 | IW1-0125 |  | IW1-0124FS+6 | 2027-03-01 | 2027-03-15 | 2027-03-01 | 2027-03-15 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 4 | IW1-0126 |  | IW1-0125FS | 2027-03-03 | 2027-04-20 | 2027-03-03 | 2027-04-20 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 5 | IW1-0127 |  | IW1-0126FS | 2027-03-05 | 2027-04-15 | 2027-03-05 | 2027-04-15 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 6 | IW1-0128 |  | IW1-0127FS | 2027-03-12 | 2027-04-07 | 2027-03-12 | 2027-04-07 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 7 | IW1-0129 |  | IW1-0128FS | 2027-03-18 | 2027-04-08 | 2027-03-18 | 2027-04-02 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 8 | IW1-0130 |  | IW1-0129FS | 2027-03-25 | 2027-04-12 | 2027-03-25 | 2027-04-12 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 9 | IW1-0131 |  | IW1-0130FS | 2027-04-01 | 2027-05-25 | 2027-04-01 | 2027-05-25 | 0 | 0 | SNET | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 10 | IW1-0132 |  | IW1-0131FS | 2027-04-01 | 2027-05-07 | 2027-04-01 | 2027-05-07 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 11 | IW1-0133 |  | IW1-0132FS | 2027-04-01 | 2027-04-21 | 2027-04-01 | 2027-04-21 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 12 | IW1-0134 |  | IW1-0133FS | 2027-04-06 | 2027-05-24 | 2027-04-06 | 2027-05-06 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 13 | IW1-0135 |  | IW1-0134FS+5 | 2027-04-13 | 2027-04-30 | 2027-04-13 | 2027-04-30 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 14 | IW1-0136 |  | IW1-0135FS+8 | 2027-04-13 | 2027-06-04 | 2027-04-13 | 2027-06-04 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 15 | IW1-0137 |  | IW1-0136FS | 2027-04-19 | 2027-05-07 | 2027-04-19 | 2027-05-07 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 16 | IW1-0138 |  | IW1-0137SS | 2027-04-21 | 2027-06-18 | 2027-04-21 | 2027-06-10 | 0 | 0 | SNET | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 17 | IW1-0139 |  | IW1-0138FS | 2027-04-27 | 2027-06-08 | 2027-04-27 | 2027-05-26 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 18 | IW1-0140 |  | IW1-0139FS | 2027-04-30 | 2027-06-10 | 2027-04-30 | 2027-06-10 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 19 | IW1-0141 |  | IW1-0140FS | 2027-04-30 | 2027-06-21 | 2027-04-30 | 2027-06-11 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 20 | IW1-0142 |  | IW1-0141FS | 2027-04-30 | 2027-06-09 | 2027-04-30 | 2027-06-09 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out — Activity 21 | IW1-0143 |  | IW1-0142FS | 2027-05-05 | 2027-06-18 | 2027-05-05 | 2027-06-18 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Electrical Fit-Out | Electrical Fit-Out Complete Milestone | IW1-0144 | Completion | IW1-0143FS+3 | 2027-06-18 | 2027-06-18 | 2027-06-18 | 2027-06-18 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 1 | IW1-0145 |  | IW1-0144FS | 2027-06-22 | 2027-08-05 | 2027-06-22 | 2027-08-05 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 2 | IW1-0146 |  | IW1-0145FS | 2027-06-25 | 2027-08-03 | 2027-06-25 | 2027-08-03 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 3 | IW1-0147 |  | IW1-0146FS | 2027-06-30 | 2027-08-31 | 2027-06-30 | 2027-08-23 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 4 | IW1-0148 |  | IW1-0147FS | 2027-07-02 | 2027-07-14 | 2027-07-02 | 2027-07-14 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 5 | IW1-0149 |  | IW1-0148FS | 2027-07-09 | 2027-08-04 | 2027-07-09 | 2027-08-04 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 6 | IW1-0150 |  | IW1-0149FS | 2027-07-14 | 2027-08-09 | 2027-07-14 | 2027-08-09 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 7 | IW1-0151 |  | IW1-0150FS | 2027-07-20 | 2027-09-13 | 2027-07-20 | 2027-09-13 | 0 | 0 | MSO | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 8 | IW1-0152 |  | IW1-0151FS | 2027-07-22 | 2027-09-06 | 2027-07-22 | 2027-09-06 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 9 | IW1-0153 |  | IW1-0152SS | 2027-07-26 | 2027-08-17 | 2027-07-26 | 2027-08-17 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 10 | IW1-0154 |  | IW1-0153FS | 2027-07-28 | 2027-09-06 | 2027-07-28 | 2027-09-06 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Fire Protection — Activity 11 | IW1-0155 |  | IW1-0154FS | 2027-07-30 | 2027-09-14 | 2027-07-30 | 2027-09-14 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | IW1-0156 | Inspection | IW1-0155FS | 2027-09-14 | 2027-09-14 | 2027-09-14 | 2027-09-14 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | IW1-0157 | Inspection | IW1-0156FS | 2027-09-14 | 2027-09-14 | 2027-09-14 | 2027-09-14 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 1 | IW1-0158 |  | IW1-0157FS | 2027-09-15 | 2027-11-02 | 2027-09-15 | 2027-11-02 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 2 | IW1-0159 |  | IW1-0158FS | 2027-09-17 | 2027-10-20 | 2027-09-17 | 2027-10-20 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 3 | IW1-0160 |  | IW1-0159FS | 2027-09-23 | 2027-11-16 | 2027-09-23 | 2027-11-16 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 4 | IW1-0161 |  | IW1-0160FS | 2027-09-27 | 2027-10-11 | 2027-09-27 | 2027-10-11 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 5 | IW1-0162 |  | IW1-0161FS | 2027-10-04 | 2027-11-04 | 2027-10-04 | 2027-11-04 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 6 | IW1-0163 |  | IW1-0162FS+4 | 2027-10-06 | 2027-11-22 | 2027-10-06 | 2027-11-22 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 7 | IW1-0164 |  | IW1-0163FS | 2027-10-11 | 2027-11-10 | 2027-10-11 | 2027-11-10 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 8 | IW1-0165 |  | IW1-0164FS | 2027-10-11 | 2027-11-22 | 2027-10-11 | 2027-11-22 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 9 | IW1-0166 |  | IW1-0165FS | 2027-10-13 | 2027-11-05 | 2027-10-13 | 2027-11-05 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 10 | IW1-0167 |  | IW1-0166FS+2 | 2027-10-18 | 2027-11-05 | 2027-10-18 | 2027-11-05 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 11 | IW1-0168 |  | IW1-0167FS | 2027-10-20 | 2027-11-02 | 2027-10-20 | 2027-11-02 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Testing — Activity 12 | IW1-0169 |  | IW1-0168FS | 2027-10-26 | 2027-11-22 | 2027-10-26 | 2027-11-22 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | IW1-0170 | Inspection | IW1-0169FS | 2027-11-22 | 2027-11-22 | 2027-11-22 | 2027-11-22 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | IW1-0171 | Inspection | IW1-0170FS | 2027-11-22 | 2027-11-22 | 2027-11-22 | 2027-11-22 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 1 | IW1-0172 |  | IW1-0171FS | 2027-11-23 | 2027-12-01 | 2027-11-23 | 2027-12-01 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 2 | IW1-0173 |  | IW1-0172FS | 2027-11-23 | 2027-12-09 | 2027-11-23 | 2027-12-09 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 3 | IW1-0174 |  | IW1-0173FS | 2027-11-30 | 2027-12-09 | 2027-11-30 | 2027-12-09 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 4 | IW1-0175 |  | IW1-0174FS | 2027-12-06 | 2027-12-29 | 2027-12-06 | 2027-12-14 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 5 | IW1-0176 |  | IW1-0175FS | 2027-12-10 | 2028-01-04 | 2027-12-10 | 2027-12-24 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 6 | IW1-0177 |  | IW1-0176FS | 2027-12-16 | 2027-12-23 | 2027-12-16 | 2027-12-23 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist — Activity 7 | IW1-0178 |  | IW1-0177FS | 2027-12-20 | 2028-01-06 | 2027-12-20 | 2028-01-06 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Inspection Milestone — Punchlist & Turnover | IW1-0179 | Inspection | IW1-0178FS | 2028-01-06 | 2028-01-06 | 2028-01-06 | 2028-01-06 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 1 | Punchlist & Turnover | Punchlist & Turnover Complete Milestone | IW1-0180 | Completion | IW1-0179FS | 2028-01-06 | 2028-01-06 | 2028-01-06 | 2028-01-06 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Tom Blackwell
Ironwood Data Hall 2 | Permitting & Approvals | Permitting — Activity 1 | IW2-0001 |  |  | 2025-09-01 | 2025-09-29 | 2025-09-01 | 2025-09-29 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Permitting & Approvals | Permitting — Activity 2 | IW2-0002 |  | IW2-0001FS | 2025-09-02 | 2025-10-03 | 2025-09-02 | 2025-09-29 | 100 | 98 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Permitting & Approvals | Permitting — Activity 3 | IW2-0003 |  | IW2-0002FS | 2025-09-08 | 2025-10-06 | 2025-09-08 | 2025-10-06 | 100 | 99 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Permitting & Approvals | Permitting — Activity 4 | IW2-0004 |  | IW2-0003FS | 2025-09-15 | 2025-09-23 | 2025-09-15 | 2025-09-23 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Permitting & Approvals | Permit Milestone — Permitting & Approvals | IW2-0005 | Permit | IW2-0004FF | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Permitting & Approvals | Permit Milestone — Permitting & Approvals | IW2-0006 | Permit | IW2-0005FF | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 1 | IW2-0007 |  | IW2-0006FS | 2025-10-09 | 2025-11-20 | 2025-10-09 | 2025-11-20 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 2 | IW2-0008 |  | IW2-0007FS | 2025-10-10 | 2025-11-03 | 2025-10-10 | 2025-11-03 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 3 | IW2-0009 |  | IW2-0008FS | 2025-10-14 | 2025-11-07 | 2025-10-14 | 2025-11-07 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 4 | IW2-0010 |  | IW2-0009FS | 2025-10-15 | 2025-11-04 | 2025-10-15 | 2025-11-04 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 5 | IW2-0011 |  | IW2-0010FS | 2025-10-22 | 2025-11-13 | 2025-10-22 | 2025-11-13 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 6 | IW2-0012 |  | IW2-0011FS+8 | 2025-10-27 | 2025-12-22 | 2025-10-27 | 2025-12-08 | 100 | 97 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 7 | IW2-0013 |  | IW2-0012SS | 2025-11-03 | 2025-12-29 | 2025-11-03 | 2025-12-29 | 100 | 99 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 8 | IW2-0014 |  | IW2-0013SS | 2025-11-10 | 2025-12-04 | 2025-11-10 | 2025-11-18 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 9 | IW2-0015 |  | IW2-0014FS | 2025-11-12 | 2026-01-06 | 2025-11-12 | 2026-01-06 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 10 | IW2-0016 |  | IW2-0015FS | 2025-11-19 | 2025-12-30 | 2025-11-19 | 2025-12-30 | 100 | 97 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 11 | IW2-0017 |  | IW2-0016FF | 2025-11-24 | 2025-12-18 | 2025-11-24 | 2025-12-18 | 100 | 98 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 12 | IW2-0018 |  | IW2-0017SS+4 | 2025-11-25 | 2026-01-01 | 2025-11-25 | 2026-01-01 | 100 | 99 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 13 | IW2-0019 |  | IW2-0018FS | 2025-11-25 | 2025-12-19 | 2025-11-25 | 2025-12-19 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 14 | IW2-0020 |  | IW2-0019FS | 2025-11-25 | 2025-12-15 | 2025-11-25 | 2025-12-15 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework — Activity 15 | IW2-0021 |  | IW2-0020FS | 2025-12-02 | 2025-12-12 | 2025-12-02 | 2025-12-12 | 100 | 100 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Sitework & Civil | Sitework & Civil Complete Milestone | IW2-0022 | Completion | IW2-0021FS | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 100 | 99 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 1 | IW2-0023 |  | IW2-0022FS | 2026-01-07 | 2026-02-20 | 2026-01-07 | 2026-02-20 | 100 | 98 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 2 | IW2-0024 |  | IW2-0023FS | 2026-01-07 | 2026-01-30 | 2026-01-07 | 2026-01-30 | 100 | 100 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 3 | IW2-0025 |  | IW2-0024FS | 2026-01-12 | 2026-02-04 | 2026-01-12 | 2026-02-04 | 100 | 98 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 4 | IW2-0026 |  | IW2-0025FS | 2026-01-14 | 2026-02-27 | 2026-01-14 | 2026-02-27 | 100 | 97 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 5 | IW2-0027 |  | IW2-0026FS | 2026-01-21 | 2026-03-09 | 2026-01-21 | 2026-02-25 | 95 | 97 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 6 | IW2-0028 |  | IW2-0027FS | 2026-01-26 | 2026-02-26 | 2026-01-26 | 2026-02-26 | 100 | 97 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 7 | IW2-0029 |  | IW2-0028FS | 2026-01-27 | 2026-03-06 | 2026-01-27 | 2026-03-06 | 100 | 98 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 8 | IW2-0030 |  | IW2-0029FS | 2026-01-27 | 2026-02-12 | 2026-01-27 | 2026-02-12 | 100 | 100 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 9 | IW2-0031 |  | IW2-0030FS | 2026-01-29 | 2026-03-26 | 2026-01-29 | 2026-03-26 | 74 | 76 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 10 | IW2-0032 |  | IW2-0031FF | 2026-02-02 | 2026-03-03 | 2026-02-02 | 2026-02-24 | 100 | 100 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 11 | IW2-0033 |  | IW2-0032FS | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-20 | 100 | 97 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations — Activity 12 | IW2-0034 |  | IW2-0033FS | 2026-02-09 | 2026-03-02 | 2026-02-09 | 2026-03-02 | 100 | 98 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Foundations | Foundations Complete Milestone | IW2-0035 | Completion | IW2-0034FS+5 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 100 | 100 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 1 | IW2-0036 |  | IW2-0035FS | 2026-03-31 | 2026-05-04 | 2026-03-31 | 2026-05-04 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 2 | IW2-0037 |  | IW2-0036FS | 2026-03-31 | 2026-04-21 | 2026-03-31 | 2026-04-21 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 3 | IW2-0038 |  | IW2-0037FS | 2026-04-03 | 2026-04-21 | 2026-04-03 | 2026-04-21 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 4 | IW2-0039 |  | IW2-0038SS | 2026-04-07 | 2026-05-01 | 2026-04-07 | 2026-05-01 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 5 | IW2-0040 |  | IW2-0039FS | 2026-04-07 | 2026-06-05 | 2026-04-07 | 2026-06-01 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 6 | IW2-0041 |  | IW2-0040FS | 2026-04-13 | 2026-04-27 | 2026-04-13 | 2026-04-27 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 7 | IW2-0042 |  | IW2-0041FS | 2026-04-20 | 2026-06-05 | 2026-04-20 | 2026-06-05 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 8 | IW2-0043 |  | IW2-0042FS+5 | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-05-06 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 9 | IW2-0044 |  | IW2-0043FS+3 | 2026-04-23 | 2026-05-29 | 2026-04-23 | 2026-05-29 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 10 | IW2-0045 |  | IW2-0044FF | 2026-04-28 | 2026-05-29 | 2026-04-28 | 2026-05-29 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 11 | IW2-0046 |  | IW2-0045FS | 2026-04-29 | 2026-06-12 | 2026-04-29 | 2026-06-01 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 12 | IW2-0047 |  | IW2-0046FS | 2026-04-29 | 2026-06-09 | 2026-04-29 | 2026-06-09 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 13 | IW2-0048 |  | IW2-0047FS | 2026-05-04 | 2026-06-04 | 2026-05-04 | 2026-06-04 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 14 | IW2-0049 |  | IW2-0048FS | 2026-05-05 | 2026-05-19 | 2026-05-05 | 2026-05-19 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 15 | IW2-0050 |  | IW2-0049FS | 2026-05-11 | 2026-06-04 | 2026-05-11 | 2026-05-25 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel — Activity 16 | IW2-0051 |  | IW2-0050FS | 2026-05-13 | 2026-06-15 | 2026-05-13 | 2026-06-15 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Structural Steel | Structural Steel Complete Milestone | IW2-0052 | Completion | IW2-0051FS | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 1 | IW2-0053 |  | IW2-0052FS | 2026-06-18 | 2026-07-08 | 2026-06-18 | 2026-07-08 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 2 | IW2-0054 |  | IW2-0053FS | 2026-06-23 | 2026-08-12 | 2026-06-23 | 2026-07-30 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 3 | IW2-0055 |  | IW2-0054FS | 2026-06-30 | 2026-07-24 | 2026-06-30 | 2026-07-24 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 4 | IW2-0056 |  | IW2-0055FF | 2026-06-30 | 2026-07-23 | 2026-06-30 | 2026-07-23 | 0 | 0 | SNET | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 5 | IW2-0057 |  | IW2-0056SS | 2026-06-30 | 2026-07-27 | 2026-06-30 | 2026-07-27 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 6 | IW2-0058 |  | IW2-0057FS+8 | 2026-06-30 | 2026-08-20 | 2026-06-30 | 2026-08-20 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 7 | IW2-0059 |  | IW2-0058FS | 2026-07-01 | 2026-07-23 | 2026-07-01 | 2026-07-23 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 8 | IW2-0060 |  | IW2-0059SS | 2026-07-01 | 2026-08-10 | 2026-07-01 | 2026-08-03 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 9 | IW2-0061 |  | IW2-0060FS | 2026-07-01 | 2026-07-22 | 2026-07-01 | 2026-07-22 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 10 | IW2-0062 |  | IW2-0061FS | 2026-07-06 | 2026-09-02 | 2026-07-06 | 2026-08-19 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 11 | IW2-0063 |  | IW2-0062FS | 2026-07-06 | 2026-07-29 | 2026-07-06 | 2026-07-29 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope — Activity 12 | IW2-0064 |  | IW2-0063FS | 2026-07-06 | 2026-09-09 | 2026-07-06 | 2026-08-26 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Building Envelope | Building Envelope Complete Milestone | IW2-0065 | Completion | IW2-0064FS | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 1 | IW2-0066 |  | IW2-0065FS | 2026-09-11 | 2026-11-04 | 2026-09-11 | 2026-11-04 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 2 | IW2-0067 |  | IW2-0066FS | 2026-09-15 | 2026-11-10 | 2026-09-15 | 2026-11-10 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 3 | IW2-0068 |  | IW2-0067FS | 2026-09-18 | 2026-10-05 | 2026-09-18 | 2026-10-05 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 4 | IW2-0069 |  | IW2-0068FS | 2026-09-25 | 2026-10-28 | 2026-09-25 | 2026-10-28 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 5 | IW2-0070 |  | IW2-0069FF | 2026-09-29 | 2026-11-12 | 2026-09-29 | 2026-11-12 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 6 | IW2-0071 |  | IW2-0070FS | 2026-10-05 | 2026-11-26 | 2026-10-05 | 2026-11-13 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 7 | IW2-0072 |  | IW2-0071FS | 2026-10-06 | 2026-11-12 | 2026-10-06 | 2026-11-12 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 8 | IW2-0073 |  | IW2-0072FS | 2026-10-06 | 2026-11-27 | 2026-10-06 | 2026-11-27 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 9 | IW2-0074 |  | IW2-0073FS | 2026-10-06 | 2026-12-01 | 2026-10-06 | 2026-11-12 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 10 | IW2-0075 |  | IW2-0074FS | 2026-10-13 | 2026-11-25 | 2026-10-13 | 2026-11-25 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 11 | IW2-0076 |  | IW2-0075FS | 2026-10-20 | 2026-11-13 | 2026-10-20 | 2026-11-13 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 12 | IW2-0077 |  | IW2-0076FS | 2026-10-21 | 2026-12-02 | 2026-10-21 | 2026-12-02 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 13 | IW2-0078 |  | IW2-0077SS | 2026-10-22 | 2026-11-13 | 2026-10-22 | 2026-11-13 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 14 | IW2-0079 |  | IW2-0078SS | 2026-10-23 | 2026-11-06 | 2026-10-23 | 2026-11-06 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 15 | IW2-0080 |  | IW2-0079FS | 2026-10-28 | 2026-11-23 | 2026-10-28 | 2026-11-16 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 16 | IW2-0081 |  | IW2-0080FS | 2026-11-02 | 2026-12-21 | 2026-11-02 | 2026-12-10 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 17 | IW2-0082 |  | IW2-0081FS | 2026-11-02 | 2026-11-12 | 2026-11-02 | 2026-11-12 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 18 | IW2-0083 |  | IW2-0082FS | 2026-11-04 | 2026-12-18 | 2026-11-04 | 2026-12-18 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 19 | IW2-0084 |  | IW2-0083FS+2 | 2026-11-05 | 2026-12-07 | 2026-11-05 | 2026-12-07 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 20 | IW2-0085 |  | IW2-0084FS | 2026-11-09 | 2026-11-25 | 2026-11-09 | 2026-11-25 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 21 | IW2-0086 |  | IW2-0085SS | 2026-11-13 | 2026-12-24 | 2026-11-13 | 2026-12-24 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In — Activity 22 | IW2-0087 |  | IW2-0086FS | 2026-11-19 | 2026-12-15 | 2026-11-19 | 2026-12-15 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | MEP Rough-In | MEP Rough-In Complete Milestone | IW2-0088 | Completion | IW2-0087FS | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 1 | IW2-0089 |  | IW2-0088FS | 2026-12-28 | 2027-02-03 | 2026-12-28 | 2027-02-03 | 0 | 0 | MSO | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 2 | IW2-0090 |  | IW2-0089FS | 2026-12-30 | 2027-01-20 | 2026-12-30 | 2027-01-12 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 3 | IW2-0091 |  | IW2-0090FS+8 | 2026-12-31 | 2027-01-13 | 2026-12-31 | 2027-01-13 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 4 | IW2-0092 |  | IW2-0091FS | 2027-01-05 | 2027-02-26 | 2027-01-05 | 2027-02-26 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 5 | IW2-0093 |  | IW2-0092FS | 2027-01-07 | 2027-02-22 | 2027-01-07 | 2027-02-22 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 6 | IW2-0094 |  | IW2-0093FS+4 | 2027-01-08 | 2027-01-25 | 2027-01-08 | 2027-01-25 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 7 | IW2-0095 |  | IW2-0094FF | 2027-01-14 | 2027-02-26 | 2027-01-14 | 2027-02-10 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 8 | IW2-0096 |  | IW2-0095FS | 2027-01-19 | 2027-02-19 | 2027-01-19 | 2027-02-19 | 0 | 0 | SNET | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 9 | IW2-0097 |  | IW2-0096FS | 2027-01-20 | 2027-03-11 | 2027-01-20 | 2027-03-11 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 10 | IW2-0098 |  | IW2-0097FS | 2027-01-20 | 2027-03-10 | 2027-01-20 | 2027-03-10 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 11 | IW2-0099 |  | IW2-0098SS+5 | 2027-01-22 | 2027-02-25 | 2027-01-22 | 2027-02-25 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 12 | IW2-0100 |  | IW2-0099SS+7 | 2027-01-26 | 2027-03-05 | 2027-01-26 | 2027-03-05 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 13 | IW2-0101 |  | IW2-0100FS | 2027-01-26 | 2027-03-15 | 2027-01-26 | 2027-03-15 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 14 | IW2-0102 |  | IW2-0101FS | 2027-02-01 | 2027-02-19 | 2027-02-01 | 2027-02-19 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out — Activity 15 | IW2-0103 |  | IW2-0102FS | 2027-02-04 | 2027-03-10 | 2027-02-04 | 2027-03-10 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Electrical Fit-Out | Electrical Fit-Out Complete Milestone | IW2-0104 | Completion | IW2-0103FS | 2027-03-10 | 2027-03-10 | 2027-03-10 | 2027-03-10 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 1 | IW2-0105 |  | IW2-0104FS | 2027-03-18 | 2027-05-04 | 2027-03-18 | 2027-04-16 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 2 | IW2-0106 |  | IW2-0105FS | 2027-03-22 | 2027-04-30 | 2027-03-22 | 2027-04-30 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 3 | IW2-0107 |  | IW2-0106FS | 2027-03-24 | 2027-04-15 | 2027-03-24 | 2027-04-15 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 4 | IW2-0108 |  | IW2-0107SS | 2027-03-25 | 2027-04-13 | 2027-03-25 | 2027-04-13 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 5 | IW2-0109 |  | IW2-0108FS | 2027-03-25 | 2027-05-07 | 2027-03-25 | 2027-05-07 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 6 | IW2-0110 |  | IW2-0109FS | 2027-03-26 | 2027-04-08 | 2027-03-26 | 2027-04-08 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Fire Protection — Activity 7 | IW2-0111 |  | IW2-0110FS | 2027-03-30 | 2027-04-14 | 2027-03-30 | 2027-04-14 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | IW2-0112 | Inspection | IW2-0111FS | 2027-04-14 | 2027-04-14 | 2027-04-14 | 2027-04-14 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Fire Protection & Life Safety | Inspection Milestone — Fire Protection & Life Safety | IW2-0113 | Inspection | IW2-0112SS | 2027-04-14 | 2027-04-14 | 2027-04-14 | 2027-04-14 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 1 | IW2-0114 |  | IW2-0113FS | 2027-05-11 | 2027-05-28 | 2027-05-11 | 2027-05-28 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 2 | IW2-0115 |  | IW2-0114FS | 2027-05-12 | 2027-06-10 | 2027-05-12 | 2027-06-10 | 0 | 0 |  | TerraForm Earthworks | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 3 | IW2-0116 |  | IW2-0115FS | 2027-05-17 | 2027-05-27 | 2027-05-17 | 2027-05-27 | 0 | 0 | SNET | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 4 | IW2-0117 |  | IW2-0116FS | 2027-05-24 | 2027-06-30 | 2027-05-24 | 2027-06-30 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 5 | IW2-0118 |  | IW2-0117FS | 2027-05-26 | 2027-07-16 | 2027-05-26 | 2027-07-16 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 6 | IW2-0119 |  | IW2-0118FS | 2027-05-26 | 2027-06-15 | 2027-05-26 | 2027-06-15 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 7 | IW2-0120 |  | IW2-0119FS | 2027-05-28 | 2027-07-05 | 2027-05-28 | 2027-07-05 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Testing — Activity 8 | IW2-0121 |  | IW2-0120FF | 2027-06-01 | 2027-07-06 | 2027-06-01 | 2027-07-06 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | IW2-0122 | Inspection | IW2-0121SS | 2027-07-06 | 2027-07-06 | 2027-07-06 | 2027-07-06 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Testing & Commissioning | Inspection Milestone — Testing & Commissioning | IW2-0123 | Inspection | IW2-0122FS | 2027-07-06 | 2027-07-06 | 2027-07-06 | 2027-07-06 | 0 | 0 |  | Brightfield Electrical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist — Activity 1 | IW2-0124 |  | IW2-0123FS | 2027-07-20 | 2027-07-29 | 2027-07-20 | 2027-07-29 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist — Activity 2 | IW2-0125 |  | IW2-0124FS | 2027-07-26 | 2027-07-29 | 2027-07-26 | 2027-07-29 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist — Activity 3 | IW2-0126 |  | IW2-0125FS | 2027-07-26 | 2027-08-12 | 2027-07-26 | 2027-08-12 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist — Activity 4 | IW2-0127 |  | IW2-0126FS | 2027-07-27 | 2027-08-11 | 2027-07-27 | 2027-08-11 | 0 | 0 |  | ColdStream Mechanical | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist — Activity 5 | IW2-0128 |  | IW2-0127SS | 2027-07-28 | 2027-08-18 | 2027-07-28 | 2027-08-18 | 0 | 0 |  | DeepCore Foundations | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Inspection Milestone — Punchlist & Turnover | IW2-0129 | Inspection | IW2-0128FS | 2027-08-18 | 2027-08-18 | 2027-08-18 | 2027-08-18 | 0 | 0 |  | SteelRise Erectors | James Thornton | Lisa Nakamura | Priya Sharma
Ironwood Data Hall 2 | Punchlist & Turnover | Punchlist & Turnover Complete Milestone | IW2-0130 | Completion | IW2-0129FS | 2027-08-18 | 2027-08-18 | 2027-08-18 | 2027-08-18 | 0 | 0 |  | AquaGuard Fire & Plumbing | James Thornton | Lisa Nakamura | Priya Sharma

## ResourceAssignment
Task ID | Resource Name | Budgeted Work | Actual Work | Resource Capacity
RLA-0001 | Program Controls — PM Crew B [Ridgeline] | 58.9 | 58.9 | 8
RLA-0002 | Program Controls — PM Crew B [Ridgeline] | 40.2 | 40.2 | 8
RLA-0003 | Program Controls — PM Crew B [Ridgeline] | 58.1 | 58.1 | 8
RLA-0004 | Program Controls — PM Crew B [Ridgeline] | 62.7 | 62.7 | 8
RLA-0007 | Summit General Services — General Labor Crew B [Ridgeline] | 131.5 | 131.5 | 8
RLA-0008 | Summit General Services — General Labor Crew B [Ridgeline] | 58.5 | 58.5 | 8
RLA-0009 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 156 | 156 | 8
RLA-0010 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 82.4 | 82.4 | 8
RLA-0011 | Summit General Services — General Labor Crew B [Ridgeline] | 126.1 | 126.1 | 8
RLA-0012 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 117.9 | 117.9 | 8
RLA-0013 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 86.1 | 86.1 | 8
RLA-0014 | Summit General Services — General Labor Crew B [Ridgeline] | 114 | 114 | 8
RLA-0015 | Summit General Services — General Labor Crew B [Ridgeline] | 155.3 | 155.3 | 8
RLA-0016 | Summit General Services — General Labor Crew B [Ridgeline] | 98.7 | 98.7 | 8
RLA-0017 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 73.7 | 73.7 | 8
RLA-0018 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 180.3 | 180.3 | 8
RLA-0019 | Summit General Services — General Labor Crew B [Ridgeline] | 130.4 | 130.4 | 8
RLA-0020 | Summit General Services — General Labor Crew B [Ridgeline] | 167.4 | 167.4 | 8
RLA-0021 | Summit General Services — General Labor Crew B [Ridgeline] | 133.3 | 133.3 | 8
RLA-0023 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 73.7 | 73.7 | 8
RLA-0024 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 108.4 | 108.4 | 8
RLA-0025 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 57.2 | 57.2 | 8
RLA-0026 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 121.1 | 121.1 | 8
RLA-0027 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 115.2 | 115.2 | 8
RLA-0028 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 133.8 | 133.8 | 8
RLA-0029 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 158.6 | 158.6 | 8
RLA-0030 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 58.8 | 58.8 | 8
RLA-0031 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 75.6 | 75.6 | 8
RLA-0032 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 135.4 | 135.4 | 8
RLA-0033 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 154.7 | 154.7 | 8
RLA-0034 | DeepCore Foundations — Concrete Crew B [Ridgeline] | 51.2 | 51.2 | 8
RLA-0036 | SteelRise Erectors — Steel Crew A [Ridgeline] | 55.6 | 55.6 | 8
RLA-0037 | SteelRise Erectors — Steel Crew A [Ridgeline] | 135.5 | 135.5 | 8
RLA-0038 | SteelRise Erectors — Steel Crew A [Ridgeline] | 115.7 | 115.7 | 8
RLA-0038 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 80.4 | 80.4 | 8
RLA-0039 | SteelRise Erectors — Steel Crew A [Ridgeline] | 52.4 | 52.4 | 8
RLA-0040 | SteelRise Erectors — Steel Crew A [Ridgeline] | 153.8 | 153.8 | 8
RLA-0040 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 84.2 | 84.2 | 8
RLA-0041 | SteelRise Erectors — Steel Crew A [Ridgeline] | 55.8 | 55.8 | 8
RLA-0041 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 25.8 | 25.8 | 8
RLA-0042 | SteelRise Erectors — Steel Crew A [Ridgeline] | 121.4 | 121.4 | 8
RLA-0042 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 44.7 | 44.7 | 8
RLA-0043 | SteelRise Erectors — Steel Crew A [Ridgeline] | 83.3 | 83.3 | 8
RLA-0044 | SteelRise Erectors — Steel Crew A [Ridgeline] | 54.5 | 54.5 | 8
RLA-0045 | SteelRise Erectors — Steel Crew A [Ridgeline] | 170.4 | 170.4 | 8
RLA-0046 | SteelRise Erectors — Steel Crew A [Ridgeline] | 50.7 | 50.7 | 8
RLA-0047 | SteelRise Erectors — Steel Crew A [Ridgeline] | 142.4 | 142.4 | 8
RLA-0048 | SteelRise Erectors — Steel Crew A [Ridgeline] | 110.9 | 110.9 | 8
RLA-0049 | SteelRise Erectors — Steel Crew A [Ridgeline] | 84.1 | 84.1 | 8
RLA-0049 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 50 | 50 | 8
RLA-0050 | SteelRise Erectors — Steel Crew A [Ridgeline] | 109 | 109 | 8
RLA-0051 | SteelRise Erectors — Steel Crew A [Ridgeline] | 196.4 | 196.4 | 8
RLA-0051 | TerraForm Earthworks — Civil Crew A [Ridgeline] | 97.5 | 97.5 | 8
RLA-0053 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 130.5 | 96.2 | 8
RLA-0054 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 195.8 | 128.6 | 8
RLA-0055 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 92.6 | 92.6 | 8
RLA-0056 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 102.7 | 71.5 | 8
RLA-0057 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 171.8 | 62.1 | 8
RLA-0058 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 156.8 | 79.1 | 8
RLA-0059 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 191.3 | 29 | 8
RLA-0060 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 58 | 32.8 | 8
RLA-0061 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 150.1 | 28.6 | 8
RLA-0062 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 53 | 26.1 | 8
RLA-0063 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 92.1 | 19.2 | 8
RLA-0064 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 179.3 | 21.8 | 8
RLA-0066 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 137.9 | 0 | 8
RLA-0066 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 99 | 0 | 8
RLA-0066 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 93.3 | 0 | 8
RLA-0067 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 201.9 | 0 | 8
RLA-0067 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 134.8 | 0 | 8
RLA-0067 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 52.5 | 0 | 8
RLA-0068 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 84.9 | 0 | 8
RLA-0069 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 131.6 | 0 | 8
RLA-0069 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 55.5 | 0 | 8
RLA-0070 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 38.3 | 0 | 8
RLA-0071 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 74.3 | 0 | 8
RLA-0072 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 91.1 | 0 | 8
RLA-0072 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 56.7 | 0 | 8
RLA-0072 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 66.8 | 0 | 8
RLA-0073 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 35.2 | 0 | 8
RLA-0074 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 205.1 | 0 | 8
RLA-0074 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 143.6 | 0 | 8
RLA-0074 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 144.1 | 0 | 8
RLA-0075 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 123.8 | 0 | 8
RLA-0076 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 49.4 | 0 | 8
RLA-0077 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 82.4 | 0 | 8
RLA-0078 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 98.9 | 0 | 8
RLA-0078 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 74.4 | 0 | 8
RLA-0079 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 217.5 | 0 | 8
RLA-0079 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 138.6 | 0 | 8
RLA-0079 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 43.3 | 0 | 8
RLA-0080 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 199.4 | 0 | 8
RLA-0080 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 115.6 | 0 | 8
RLA-0080 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 54 | 0 | 8
RLA-0081 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 295.1 | 0 | 8
RLA-0081 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 205.2 | 0 | 8
RLA-0081 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 92.9 | 0 | 8
RLA-0082 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 80.4 | 0 | 8
RLA-0083 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 115.9 | 0 | 8
RLA-0083 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 75.9 | 0 | 8
RLA-0083 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 95.2 | 0 | 8
RLA-0084 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 229 | 0 | 8
RLA-0084 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 90 | 0 | 8
RLA-0085 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 147.6 | 0 | 8
RLA-0085 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 56.4 | 0 | 8
RLA-0086 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 171.9 | 0 | 8
RLA-0087 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 131 | 0 | 8
RLA-0089 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 145.9 | 0 | 8
RLA-0090 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 100.1 | 0 | 8
RLA-0091 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 224.7 | 0 | 8
RLA-0092 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 101.7 | 0 | 8
RLA-0093 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 96.3 | 0 | 8
RLA-0094 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 117.9 | 0 | 8
RLA-0095 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 63.6 | 0 | 8
RLA-0095 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 41.9 | 0 | 8
RLA-0096 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 127.8 | 0 | 8
RLA-0097 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 123.7 | 0 | 8
RLA-0097 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 51.8 | 0 | 8
RLA-0098 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 104.8 | 0 | 8
RLA-0099 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 146.9 | 0 | 8
RLA-0100 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 95.5 | 0 | 8
RLA-0101 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 192.3 | 0 | 8
RLA-0101 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 119.8 | 0 | 8
RLA-0102 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 233.6 | 0 | 8
RLA-0103 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 93 | 0 | 8
RLA-0105 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 259.6 | 0 | 8
RLA-0105 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 163.1 | 0 | 8
RLA-0106 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 174.5 | 0 | 8
RLA-0107 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 210.6 | 0 | 8
RLA-0107 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 135.1 | 0 | 8
RLA-0108 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 95.6 | 0 | 8
RLA-0109 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 170 | 0 | 8
RLA-0110 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 152.9 | 0 | 8
RLA-0111 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 102.8 | 0 | 8
RLA-0111 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 74.2 | 0 | 8
RLA-0114 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 65.4 | 0 | 8
RLA-0114 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 43.6 | 0 | 8
RLA-0115 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 218 | 0 | 8
RLA-0116 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 153.3 | 0 | 8
RLA-0116 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 80 | 0 | 8
RLA-0117 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 182.5 | 0 | 8
RLA-0117 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 137 | 0 | 8
RLA-0118 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 90.4 | 0 | 8
RLA-0118 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 36.1 | 0 | 8
RLA-0119 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 176.9 | 0 | 8
RLA-0119 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 68.8 | 0 | 8
RLA-0120 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 209.8 | 0 | 8
RLA-0120 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 107.6 | 0 | 8
RLA-0121 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 220.4 | 0 | 8
RLA-0121 | TechLink Automation — Controls/BMS Crew A [Ridgeline] | 95.2 | 0 | 8
RLA-0124 | Program Controls — PM Crew B [Ridgeline] | 54 | 0 | 8
RLA-0125 | Program Controls — PM Crew B [Ridgeline] | 37.1 | 0 | 8
RLA-0126 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 20.3 | 0 | 8
RLA-0127 | Program Controls — PM Crew B [Ridgeline] | 30 | 0 | 8
RLA-0128 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 64.8 | 0 | 8
RLC-0001 | Program Controls — PM Crew C [Ridgeline] | 52.7 | 52.7 | 8
RLC-0004 | Summit General Services — General Labor Crew C [Ridgeline] | 195.6 | 195.6 | 8
RLC-0005 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 143.1 | 143.1 | 8
RLC-0006 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 144.2 | 144.2 | 8
RLC-0007 | Summit General Services — General Labor Crew C [Ridgeline] | 102.6 | 102.6 | 8
RLC-0008 | Summit General Services — General Labor Crew C [Ridgeline] | 220 | 220 | 8
RLC-0009 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 96.2 | 96.2 | 8
RLC-0011 | DeepCore Foundations — Concrete Crew C [Ridgeline] | 165 | 165 | 8
RLC-0012 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 158.1 | 158.1 | 8
RLC-0013 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 98.7 | 98.7 | 8
RLC-0014 | TerraForm Earthworks — Civil Crew C [Ridgeline] | 80.4 | 80.4 | 8
RLC-0015 | DeepCore Foundations — Concrete Crew C [Ridgeline] | 133.1 | 133.1 | 8
RLC-0017 | SteelRise Erectors — Steel Crew A [Ridgeline] | 108.7 | 108.7 | 8
RLC-0018 | SteelRise Erectors — Steel Crew A [Ridgeline] | 185.8 | 185.8 | 8
RLC-0019 | SteelRise Erectors — Steel Crew A [Ridgeline] | 84.3 | 84.3 | 8
RLC-0020 | SteelRise Erectors — Steel Crew A [Ridgeline] | 189.8 | 189.8 | 8
RLC-0021 | SteelRise Erectors — Steel Crew A [Ridgeline] | 180.4 | 180.4 | 8
RLC-0022 | SteelRise Erectors — Steel Crew A [Ridgeline] | 118 | 118 | 8
RLC-0023 | SteelRise Erectors — Steel Crew A [Ridgeline] | 66.7 | 66.7 | 8
RLC-0023 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 44.9 | 44.9 | 8
RLC-0025 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 96.2 | 96.2 | 8
RLC-0026 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 39.4 | 39.4 | 8
RLC-0027 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 79 | 79 | 8
RLC-0028 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 99 | 99 | 8
RLC-0029 | Apex Building Envelope — Envelope Crew B [Ridgeline] | 94.4 | 61.6 | 8
RLC-0031 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 93.9 | 0 | 8
RLC-0031 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 72.8 | 0 | 8
RLC-0031 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 64.6 | 0 | 8
RLC-0032 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 137.5 | 0 | 8
RLC-0033 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 102.4 | 0 | 8
RLC-0033 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 51 | 0 | 8
RLC-0034 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 150.8 | 0 | 8
RLC-0034 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 85 | 0 | 8
RLC-0034 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 48.7 | 0 | 8
RLC-0035 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 135.9 | 0 | 8
RLC-0035 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 72.2 | 0 | 8
RLC-0036 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 71.6 | 0 | 8
RLC-0036 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 53.2 | 0 | 8
RLC-0037 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 166.8 | 0 | 8
RLC-0038 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 181.6 | 0 | 8
RLC-0038 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 133.9 | 0 | 8
RLC-0039 | Brightfield Electrical — Elec Rough Crew A [Ridgeline] | 177.5 | 0 | 8
RLC-0039 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 64.2 | 0 | 8
RLC-0040 | ColdStream Mechanical — Mechanical Crew A [Ridgeline] | 51.3 | 0 | 8
RLC-0040 | PrimeMEP Services — MEP Coord Crew A [Ridgeline] | 25.1 | 0 | 8
RLC-0042 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 197.9 | 0 | 8
RLC-0043 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 156.5 | 0 | 8
RLC-0044 | TechLink Automation — Controls/BMS Crew C [Ridgeline] | 70.5 | 0 | 8
RLC-0044 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 54.6 | 0 | 8
RLC-0045 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 253.2 | 0 | 8
RLC-0045 | TechLink Automation — Controls/BMS Crew C [Ridgeline] | 92.7 | 0 | 8
RLC-0046 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 155.2 | 0 | 8
RLC-0047 | Brightfield Electrical — Elec Fit-Out Crew C [Ridgeline] | 87.4 | 0 | 8
RLC-0049 | AquaGuard Fire & Plumbing — Plumbing/FP Crew A [Ridgeline] | 99 | 0 | 8
RLC-0050 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 108.9 | 0 | 8
RLC-0053 | TechLink Automation — Controls/BMS Crew C [Ridgeline] | 242.7 | 0 | 8
RLC-0053 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 98.7 | 0 | 8
RLC-0054 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 55 | 0 | 8
RLC-0055 | Pinnacle Commissioning — Commissioning Crew A [Ridgeline] | 235.8 | 0 | 8
RLC-0058 | Meridian QA/QC — QA/QC Crew C [Ridgeline] | 52.1 | 0 | 8
IW1-0001 | Program Controls — PM Crew A [Ironwood] | 28 | 28 | 8
IW1-0002 | Program Controls — PM Crew A [Ironwood] | 26.3 | 26.3 | 8
IW1-0003 | Program Controls — PM Crew A [Ironwood] | 66.2 | 66.2 | 8
IW1-0004 | Program Controls — PM Crew A [Ironwood] | 91.7 | 91.7 | 8
IW1-0005 | Program Controls — PM Crew A [Ironwood] | 38.3 | 38.3 | 8
IW1-0006 | Program Controls — PM Crew A [Ironwood] | 53.4 | 53.4 | 8
IW1-0007 | Program Controls — PM Crew A [Ironwood] | 61.7 | 61.7 | 8
IW1-0010 | Summit General Services — General Labor Crew B [Ironwood] | 51.4 | 51.4 | 8
IW1-0011 | Summit General Services — General Labor Crew B [Ironwood] | 82.7 | 82.7 | 8
IW1-0012 | TerraForm Earthworks — Civil Crew A [Ironwood] | 198.4 | 198.4 | 8
IW1-0013 | TerraForm Earthworks — Civil Crew A [Ironwood] | 97.8 | 97.8 | 8
IW1-0014 | TerraForm Earthworks — Civil Crew A [Ironwood] | 39.9 | 39.9 | 8
IW1-0015 | Summit General Services — General Labor Crew B [Ironwood] | 100.8 | 100.8 | 8
IW1-0016 | TerraForm Earthworks — Civil Crew A [Ironwood] | 117.6 | 117.6 | 8
IW1-0017 | TerraForm Earthworks — Civil Crew A [Ironwood] | 119.5 | 119.5 | 8
IW1-0018 | Summit General Services — General Labor Crew B [Ironwood] | 215 | 215 | 8
IW1-0019 | TerraForm Earthworks — Civil Crew A [Ironwood] | 45.3 | 45.3 | 8
IW1-0020 | TerraForm Earthworks — Civil Crew A [Ironwood] | 153.6 | 153.6 | 8
IW1-0021 | Summit General Services — General Labor Crew B [Ironwood] | 109 | 109 | 8
IW1-0022 | TerraForm Earthworks — Civil Crew A [Ironwood] | 198.7 | 198.7 | 8
IW1-0023 | Summit General Services — General Labor Crew B [Ironwood] | 108.5 | 108.5 | 8
IW1-0024 | Summit General Services — General Labor Crew B [Ironwood] | 104.9 | 104.9 | 8
IW1-0025 | TerraForm Earthworks — Civil Crew A [Ironwood] | 149.9 | 149.9 | 8
IW1-0026 | Summit General Services — General Labor Crew B [Ironwood] | 32.2 | 32.2 | 8
IW1-0027 | TerraForm Earthworks — Civil Crew A [Ironwood] | 79.2 | 79.2 | 8
IW1-0028 | Summit General Services — General Labor Crew B [Ironwood] | 163.9 | 163.9 | 8
IW1-0029 | TerraForm Earthworks — Civil Crew A [Ironwood] | 48.8 | 48.8 | 8
IW1-0030 | TerraForm Earthworks — Civil Crew A [Ironwood] | 223.3 | 223.3 | 8
IW1-0032 | TerraForm Earthworks — Civil Crew A [Ironwood] | 124.2 | 124.2 | 8
IW1-0033 | DeepCore Foundations — Concrete Crew A [Ironwood] | 142.2 | 142.2 | 8
IW1-0034 | TerraForm Earthworks — Civil Crew A [Ironwood] | 160.8 | 160.8 | 8
IW1-0035 | TerraForm Earthworks — Civil Crew A [Ironwood] | 91.4 | 91.4 | 8
IW1-0036 | TerraForm Earthworks — Civil Crew A [Ironwood] | 128.3 | 128.3 | 8
IW1-0037 | TerraForm Earthworks — Civil Crew A [Ironwood] | 169.5 | 169.5 | 8
IW1-0038 | TerraForm Earthworks — Civil Crew A [Ironwood] | 210.1 | 210.1 | 8
IW1-0039 | TerraForm Earthworks — Civil Crew A [Ironwood] | 71.4 | 71.4 | 8
IW1-0040 | TerraForm Earthworks — Civil Crew A [Ironwood] | 237.7 | 237.7 | 8
IW1-0041 | DeepCore Foundations — Concrete Crew A [Ironwood] | 129.5 | 129.5 | 8
IW1-0042 | TerraForm Earthworks — Civil Crew A [Ironwood] | 144.9 | 144.9 | 8
IW1-0043 | DeepCore Foundations — Concrete Crew A [Ironwood] | 123.6 | 123.6 | 8
IW1-0044 | TerraForm Earthworks — Civil Crew A [Ironwood] | 59.5 | 59.5 | 8
IW1-0045 | TerraForm Earthworks — Civil Crew A [Ironwood] | 97.5 | 97.5 | 8
IW1-0046 | TerraForm Earthworks — Civil Crew A [Ironwood] | 82.1 | 82.1 | 8
IW1-0047 | TerraForm Earthworks — Civil Crew A [Ironwood] | 36.6 | 36.6 | 8
IW1-0048 | TerraForm Earthworks — Civil Crew A [Ironwood] | 53.5 | 53.5 | 8
IW1-0050 | SteelRise Erectors — Steel Crew A [Ironwood] | 67.8 | 67.8 | 8
IW1-0051 | SteelRise Erectors — Steel Crew A [Ironwood] | 68.7 | 68.7 | 8
IW1-0052 | SteelRise Erectors — Steel Crew A [Ironwood] | 93.9 | 93.9 | 8
IW1-0052 | DeepCore Foundations — Concrete Crew A [Ironwood] | 69.7 | 69.7 | 8
IW1-0053 | SteelRise Erectors — Steel Crew A [Ironwood] | 128.6 | 128.6 | 8
IW1-0054 | SteelRise Erectors — Steel Crew A [Ironwood] | 203.6 | 176.6 | 8
IW1-0055 | SteelRise Erectors — Steel Crew A [Ironwood] | 119.7 | 119.7 | 8
IW1-0056 | SteelRise Erectors — Steel Crew A [Ironwood] | 184.8 | 153.7 | 8
IW1-0057 | SteelRise Erectors — Steel Crew A [Ironwood] | 138.9 | 138.9 | 8
IW1-0058 | SteelRise Erectors — Steel Crew A [Ironwood] | 166.4 | 148.8 | 8
IW1-0059 | SteelRise Erectors — Steel Crew A [Ironwood] | 139.9 | 121.7 | 8
IW1-0059 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 113.4 | 93.4 | 8
IW1-0060 | SteelRise Erectors — Steel Crew A [Ironwood] | 121.8 | 76 | 8
IW1-0061 | SteelRise Erectors — Steel Crew A [Ironwood] | 167 | 80.5 | 8
IW1-0062 | SteelRise Erectors — Steel Crew A [Ironwood] | 165.2 | 82.3 | 8
IW1-0063 | SteelRise Erectors — Steel Crew A [Ironwood] | 177 | 107.3 | 8
IW1-0064 | SteelRise Erectors — Steel Crew A [Ironwood] | 139.3 | 69.5 | 8
IW1-0065 | SteelRise Erectors — Steel Crew A [Ironwood] | 56.6 | 47.5 | 8
IW1-0066 | SteelRise Erectors — Steel Crew A [Ironwood] | 174.3 | 33.6 | 8
IW1-0067 | SteelRise Erectors — Steel Crew A [Ironwood] | 92.3 | 9.9 | 8
IW1-0068 | SteelRise Erectors — Steel Crew A [Ironwood] | 233.8 | 0 | 8
IW1-0068 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 154.6 | 0 | 8
IW1-0069 | SteelRise Erectors — Steel Crew A [Ironwood] | 64 | 0 | 8
IW1-0070 | SteelRise Erectors — Steel Crew A [Ironwood] | 189.9 | 0 | 8
IW1-0071 | SteelRise Erectors — Steel Crew A [Ironwood] | 52.9 | 0 | 8
IW1-0073 | Apex Building Envelope — Envelope Crew B [Ironwood] | 143.6 | 0 | 8
IW1-0074 | Apex Building Envelope — Envelope Crew B [Ironwood] | 136.2 | 0 | 8
IW1-0075 | Apex Building Envelope — Envelope Crew B [Ironwood] | 93.6 | 0 | 8
IW1-0076 | Apex Building Envelope — Envelope Crew B [Ironwood] | 89.3 | 0 | 8
IW1-0077 | Apex Building Envelope — Envelope Crew B [Ironwood] | 110.4 | 0 | 8
IW1-0078 | Apex Building Envelope — Envelope Crew B [Ironwood] | 104.2 | 0 | 8
IW1-0079 | Apex Building Envelope — Envelope Crew B [Ironwood] | 188.4 | 0 | 8
IW1-0080 | Apex Building Envelope — Envelope Crew B [Ironwood] | 105.3 | 0 | 8
IW1-0081 | Apex Building Envelope — Envelope Crew B [Ironwood] | 196 | 0 | 8
IW1-0082 | Apex Building Envelope — Envelope Crew B [Ironwood] | 57 | 0 | 8
IW1-0083 | Apex Building Envelope — Envelope Crew B [Ironwood] | 39.9 | 0 | 8
IW1-0084 | Apex Building Envelope — Envelope Crew B [Ironwood] | 109.8 | 0 | 8
IW1-0085 | Apex Building Envelope — Envelope Crew B [Ironwood] | 107.5 | 0 | 8
IW1-0086 | Apex Building Envelope — Envelope Crew B [Ironwood] | 44.1 | 0 | 8
IW1-0087 | Apex Building Envelope — Envelope Crew B [Ironwood] | 66.6 | 0 | 8
IW1-0088 | Apex Building Envelope — Envelope Crew B [Ironwood] | 101.8 | 0 | 8
IW1-0089 | Apex Building Envelope — Envelope Crew B [Ironwood] | 206.8 | 0 | 8
IW1-0091 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 122.1 | 0 | 8
IW1-0091 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 89.8 | 0 | 8
IW1-0092 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 278.8 | 0 | 8
IW1-0092 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 160.6 | 0 | 8
IW1-0092 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 140 | 0 | 8
IW1-0093 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 41.3 | 0 | 8
IW1-0094 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 42.6 | 0 | 8
IW1-0095 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 222.4 | 0 | 8
IW1-0095 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 136.7 | 0 | 8
IW1-0095 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 117.9 | 0 | 8
IW1-0096 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 151.7 | 0 | 8
IW1-0096 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 79.2 | 0 | 8
IW1-0097 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 243.6 | 0 | 8
IW1-0097 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 164 | 0 | 8
IW1-0097 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 89.9 | 0 | 8
IW1-0098 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 158.6 | 0 | 8
IW1-0098 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 106.3 | 0 | 8
IW1-0098 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 54.4 | 0 | 8
IW1-0099 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 138.3 | 0 | 8
IW1-0099 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 72.4 | 0 | 8
IW1-0100 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 209.6 | 0 | 8
IW1-0100 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 99.8 | 0 | 8
IW1-0101 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 149.3 | 0 | 8
IW1-0101 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 69 | 0 | 8
IW1-0101 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 55.4 | 0 | 8
IW1-0102 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 32.2 | 0 | 8
IW1-0102 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 24.5 | 0 | 8
IW1-0103 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 260.2 | 0 | 8
IW1-0103 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 141.9 | 0 | 8
IW1-0103 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 99.4 | 0 | 8
IW1-0104 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 64.9 | 0 | 8
IW1-0105 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 235.7 | 0 | 8
IW1-0105 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 93.7 | 0 | 8
IW1-0106 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 152.7 | 0 | 8
IW1-0107 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 53.8 | 0 | 8
IW1-0107 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 40.8 | 0 | 8
IW1-0108 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 133.8 | 0 | 8
IW1-0108 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 113.2 | 0 | 8
IW1-0108 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 82.3 | 0 | 8
IW1-0109 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 78.3 | 0 | 8
IW1-0109 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 47.3 | 0 | 8
IW1-0109 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 55.4 | 0 | 8
IW1-0110 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 115.5 | 0 | 8
IW1-0110 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 47.7 | 0 | 8
IW1-0111 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 63.3 | 0 | 8
IW1-0111 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 42.5 | 0 | 8
IW1-0111 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 27.5 | 0 | 8
IW1-0112 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 107.5 | 0 | 8
IW1-0113 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 86.4 | 0 | 8
IW1-0114 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 180 | 0 | 8
IW1-0115 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 141.8 | 0 | 8
IW1-0115 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 112 | 0 | 8
IW1-0115 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 95.5 | 0 | 8
IW1-0116 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 166.2 | 0 | 8
IW1-0116 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 110 | 0 | 8
IW1-0116 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 94.3 | 0 | 8
IW1-0117 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 145.7 | 0 | 8
IW1-0117 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 93.5 | 0 | 8
IW1-0118 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 66.2 | 0 | 8
IW1-0118 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 53.4 | 0 | 8
IW1-0119 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 113.9 | 0 | 8
IW1-0120 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 89.1 | 0 | 8
IW1-0121 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 136.7 | 0 | 8
IW1-0123 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 95.2 | 0 | 8
IW1-0124 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 92.6 | 0 | 8
IW1-0124 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 64.3 | 0 | 8
IW1-0125 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 62.7 | 0 | 8
IW1-0125 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 28.1 | 0 | 8
IW1-0126 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 137.8 | 0 | 8
IW1-0127 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 138.3 | 0 | 8
IW1-0128 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 107.9 | 0 | 8
IW1-0129 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 96.8 | 0 | 8
IW1-0129 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 38.2 | 0 | 8
IW1-0130 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 75.1 | 0 | 8
IW1-0130 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 39.3 | 0 | 8
IW1-0131 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 208.2 | 0 | 8
IW1-0132 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 147.3 | 0 | 8
IW1-0133 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 71.5 | 0 | 8
IW1-0134 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 215.9 | 0 | 8
IW1-0134 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 100.9 | 0 | 8
IW1-0135 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 75.8 | 0 | 8
IW1-0136 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 174.6 | 0 | 8
IW1-0137 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 72 | 0 | 8
IW1-0138 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 288.5 | 0 | 8
IW1-0138 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 162.6 | 0 | 8
IW1-0139 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 145.5 | 0 | 8
IW1-0140 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 119.9 | 0 | 8
IW1-0141 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 306.8 | 0 | 8
IW1-0141 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 108.5 | 0 | 8
IW1-0142 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 103 | 0 | 8
IW1-0143 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 191.5 | 0 | 8
IW1-0143 | Brightfield Electrical — Elec Fit-Out Crew B [Ironwood] | 127.7 | 0 | 8
IW1-0145 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 136.9 | 0 | 8
IW1-0146 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 161 | 0 | 8
IW1-0146 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 64.1 | 0 | 8
IW1-0147 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 195.1 | 0 | 8
IW1-0148 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 27.1 | 0 | 8
IW1-0149 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 97.8 | 0 | 8
IW1-0150 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 90.1 | 0 | 8
IW1-0151 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 198.7 | 0 | 8
IW1-0152 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 174.2 | 0 | 8
IW1-0152 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 126.2 | 0 | 8
IW1-0153 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 133.6 | 0 | 8
IW1-0153 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 57.1 | 0 | 8
IW1-0154 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 160.6 | 0 | 8
IW1-0154 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 116.5 | 0 | 8
IW1-0155 | AquaGuard Fire & Plumbing — Plumbing/FP Crew C [Ironwood] | 138 | 0 | 8
IW1-0158 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 175.8 | 0 | 8
IW1-0158 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 122.3 | 0 | 8
IW1-0159 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 129 | 0 | 8
IW1-0159 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 73.8 | 0 | 8
IW1-0160 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 181.1 | 0 | 8
IW1-0160 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 126.8 | 0 | 8
IW1-0161 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 39.2 | 0 | 8
IW1-0162 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 111 | 0 | 8
IW1-0163 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 124.2 | 0 | 8
IW1-0164 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 70.5 | 0 | 8
IW1-0165 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 181 | 0 | 8
IW1-0166 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 105.9 | 0 | 8
IW1-0166 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 65.9 | 0 | 8
IW1-0167 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 95.7 | 0 | 8
IW1-0167 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 44.3 | 0 | 8
IW1-0168 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 33.3 | 0 | 8
IW1-0169 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 101.6 | 0 | 8
IW1-0169 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 82.5 | 0 | 8
IW1-0172 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 38.6 | 0 | 8
IW1-0173 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 56.5 | 0 | 8
IW1-0174 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 29.8 | 0 | 8
IW1-0175 | Program Controls — PM Crew A [Ironwood] | 95.3 | 0 | 8
IW1-0176 | Program Controls — PM Crew A [Ironwood] | 68.3 | 0 | 8
IW1-0177 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 29.6 | 0 | 8
IW1-0178 | Program Controls — PM Crew A [Ironwood] | 55.5 | 0 | 8
IW2-0001 | Program Controls — PM Crew B [Ironwood] | 101.3 | 101.3 | 8
IW2-0002 | Program Controls — PM Crew B [Ironwood] | 94.1 | 94.1 | 8
IW2-0003 | Program Controls — PM Crew B [Ironwood] | 95.8 | 95.8 | 8
IW2-0004 | Program Controls — PM Crew B [Ironwood] | 37.5 | 37.5 | 8
IW2-0007 | Summit General Services — General Labor Crew A [Ironwood] | 182.3 | 182.3 | 8
IW2-0008 | TerraForm Earthworks — Civil Crew B [Ironwood] | 106.5 | 106.5 | 8
IW2-0009 | TerraForm Earthworks — Civil Crew B [Ironwood] | 80.6 | 80.6 | 8
IW2-0010 | TerraForm Earthworks — Civil Crew B [Ironwood] | 51.6 | 51.6 | 8
IW2-0011 | TerraForm Earthworks — Civil Crew B [Ironwood] | 74.8 | 74.8 | 8
IW2-0012 | Summit General Services — General Labor Crew A [Ironwood] | 256.3 | 256.3 | 8
IW2-0013 | Summit General Services — General Labor Crew A [Ironwood] | 155.3 | 155.3 | 8
IW2-0014 | TerraForm Earthworks — Civil Crew B [Ironwood] | 93.8 | 93.8 | 8
IW2-0015 | TerraForm Earthworks — Civil Crew B [Ironwood] | 195.2 | 195.2 | 8
IW2-0016 | TerraForm Earthworks — Civil Crew B [Ironwood] | 148.1 | 148.1 | 8
IW2-0017 | TerraForm Earthworks — Civil Crew B [Ironwood] | 93.2 | 93.2 | 8
IW2-0018 | TerraForm Earthworks — Civil Crew B [Ironwood] | 116.4 | 116.4 | 8
IW2-0019 | TerraForm Earthworks — Civil Crew B [Ironwood] | 80.7 | 80.7 | 8
IW2-0020 | TerraForm Earthworks — Civil Crew B [Ironwood] | 81.1 | 81.1 | 8
IW2-0021 | Summit General Services — General Labor Crew A [Ironwood] | 45.6 | 45.6 | 8
IW2-0023 | TerraForm Earthworks — Civil Crew B [Ironwood] | 109.3 | 109.3 | 8
IW2-0024 | DeepCore Foundations — Concrete Crew C [Ironwood] | 74.6 | 74.6 | 8
IW2-0025 | TerraForm Earthworks — Civil Crew B [Ironwood] | 87.7 | 87.7 | 8
IW2-0026 | DeepCore Foundations — Concrete Crew C [Ironwood] | 106.9 | 106.9 | 8
IW2-0027 | DeepCore Foundations — Concrete Crew C [Ironwood] | 164 | 148.1 | 8
IW2-0028 | TerraForm Earthworks — Civil Crew B [Ironwood] | 112.7 | 112.7 | 8
IW2-0029 | TerraForm Earthworks — Civil Crew B [Ironwood] | 112.4 | 112.4 | 8
IW2-0030 | DeepCore Foundations — Concrete Crew C [Ironwood] | 48.8 | 48.8 | 8
IW2-0031 | DeepCore Foundations — Concrete Crew C [Ironwood] | 255 | 168.8 | 8
IW2-0032 | DeepCore Foundations — Concrete Crew C [Ironwood] | 93.3 | 93.3 | 8
IW2-0033 | TerraForm Earthworks — Civil Crew B [Ironwood] | 67.9 | 67.9 | 8
IW2-0034 | TerraForm Earthworks — Civil Crew B [Ironwood] | 95.3 | 95.3 | 8
IW2-0036 | SteelRise Erectors — Steel Crew A [Ironwood] | 130.7 | 0 | 8
IW2-0037 | SteelRise Erectors — Steel Crew A [Ironwood] | 81.6 | 0 | 8
IW2-0038 | SteelRise Erectors — Steel Crew A [Ironwood] | 57.6 | 0 | 8
IW2-0039 | SteelRise Erectors — Steel Crew A [Ironwood] | 91.1 | 0 | 8
IW2-0040 | SteelRise Erectors — Steel Crew A [Ironwood] | 202.9 | 0 | 8
IW2-0041 | SteelRise Erectors — Steel Crew A [Ironwood] | 40.9 | 0 | 8
IW2-0042 | SteelRise Erectors — Steel Crew A [Ironwood] | 149.1 | 0 | 8
IW2-0043 | SteelRise Erectors — Steel Crew A [Ironwood] | 66.7 | 0 | 8
IW2-0044 | SteelRise Erectors — Steel Crew A [Ironwood] | 97 | 0 | 8
IW2-0045 | SteelRise Erectors — Steel Crew A [Ironwood] | 116.6 | 0 | 8
IW2-0045 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 65.5 | 0 | 8
IW2-0046 | SteelRise Erectors — Steel Crew A [Ironwood] | 148.9 | 0 | 8
IW2-0047 | SteelRise Erectors — Steel Crew A [Ironwood] | 128.2 | 0 | 8
IW2-0048 | SteelRise Erectors — Steel Crew A [Ironwood] | 125.7 | 0 | 8
IW2-0048 | Ashford Coatings — Painting Crew A [Ironwood] | 66.3 | 0 | 8
IW2-0049 | SteelRise Erectors — Steel Crew A [Ironwood] | 44.3 | 0 | 8
IW2-0050 | SteelRise Erectors — Steel Crew A [Ironwood] | 92.4 | 0 | 8
IW2-0051 | SteelRise Erectors — Steel Crew A [Ironwood] | 126.2 | 0 | 8
IW2-0051 | DeepCore Foundations — Concrete Crew C [Ironwood] | 99.1 | 0 | 8
IW2-0053 | Apex Building Envelope — Envelope Crew A [Ironwood] | 53.4 | 0 | 8
IW2-0054 | Apex Building Envelope — Envelope Crew A [Ironwood] | 166 | 0 | 8
IW2-0055 | Apex Building Envelope — Envelope Crew A [Ironwood] | 65 | 0 | 8
IW2-0056 | Apex Building Envelope — Envelope Crew A [Ironwood] | 67.7 | 0 | 8
IW2-0057 | Apex Building Envelope — Envelope Crew A [Ironwood] | 80.6 | 0 | 8
IW2-0058 | Apex Building Envelope — Envelope Crew A [Ironwood] | 162.4 | 0 | 8
IW2-0059 | Apex Building Envelope — Envelope Crew A [Ironwood] | 67.8 | 0 | 8
IW2-0060 | Apex Building Envelope — Envelope Crew A [Ironwood] | 89 | 0 | 8
IW2-0061 | Apex Building Envelope — Envelope Crew A [Ironwood] | 62.6 | 0 | 8
IW2-0062 | Apex Building Envelope — Envelope Crew A [Ironwood] | 150.8 | 0 | 8
IW2-0063 | Apex Building Envelope — Envelope Crew A [Ironwood] | 68.4 | 0 | 8
IW2-0064 | Apex Building Envelope — Envelope Crew A [Ironwood] | 240.8 | 0 | 8
IW2-0066 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 227.7 | 0 | 8
IW2-0066 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 81.6 | 0 | 8
IW2-0067 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 226.8 | 0 | 8
IW2-0067 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 164.4 | 0 | 8
IW2-0067 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 162.3 | 0 | 8
IW2-0068 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 54.7 | 0 | 8
IW2-0069 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 94.2 | 0 | 8
IW2-0070 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 277.1 | 0 | 8
IW2-0070 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 99 | 0 | 8
IW2-0071 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 334.2 | 0 | 8
IW2-0071 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 203.5 | 0 | 8
IW2-0071 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 141.4 | 0 | 8
IW2-0072 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 114.6 | 0 | 8
IW2-0072 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 80.1 | 0 | 8
IW2-0073 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 256.6 | 0 | 8
IW2-0073 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 148.9 | 0 | 8
IW2-0074 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 209.8 | 0 | 8
IW2-0074 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 136.2 | 0 | 8
IW2-0075 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 168 | 0 | 8
IW2-0075 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 102.9 | 0 | 8
IW2-0075 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 59.4 | 0 | 8
IW2-0076 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 157.3 | 0 | 8
IW2-0076 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 95.2 | 0 | 8
IW2-0076 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 50.2 | 0 | 8
IW2-0077 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 200.2 | 0 | 8
IW2-0077 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 145.1 | 0 | 8
IW2-0077 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 104.6 | 0 | 8
IW2-0078 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 78.2 | 0 | 8
IW2-0078 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 56.7 | 0 | 8
IW2-0079 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 48.8 | 0 | 8
IW2-0079 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 38.4 | 0 | 8
IW2-0079 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 29.7 | 0 | 8
IW2-0080 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 64.5 | 0 | 8
IW2-0081 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 181.9 | 0 | 8
IW2-0082 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 69.3 | 0 | 8
IW2-0082 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 45.8 | 0 | 8
IW2-0082 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 19 | 0 | 8
IW2-0083 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 297 | 0 | 8
IW2-0083 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 176.1 | 0 | 8
IW2-0083 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 109.4 | 0 | 8
IW2-0084 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 156.9 | 0 | 8
IW2-0084 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 87.5 | 0 | 8
IW2-0085 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 72.2 | 0 | 8
IW2-0085 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 35.7 | 0 | 8
IW2-0086 | PrimeMEP Services — MEP Coord Crew A [Ironwood] | 175.4 | 0 | 8
IW2-0086 | ColdStream Mechanical — Mechanical Crew A [Ironwood] | 75.5 | 0 | 8
IW2-0087 | Brightfield Electrical — Elec Rough Crew A [Ironwood] | 69.1 | 0 | 8
IW2-0089 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 143.6 | 0 | 8
IW2-0089 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 94 | 0 | 8
IW2-0090 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 88.4 | 0 | 8
IW2-0090 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 45.5 | 0 | 8
IW2-0091 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 40.8 | 0 | 8
IW2-0092 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 149.3 | 0 | 8
IW2-0093 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 151.8 | 0 | 8
IW2-0093 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 115.8 | 0 | 8
IW2-0094 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 52.8 | 0 | 8
IW2-0095 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 190.8 | 0 | 8
IW2-0096 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 95.6 | 0 | 8
IW2-0097 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 172.1 | 0 | 8
IW2-0098 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 183.4 | 0 | 8
IW2-0099 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 154.5 | 0 | 8
IW2-0099 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 69.5 | 0 | 8
IW2-0100 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 105.6 | 0 | 8
IW2-0101 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 173.5 | 0 | 8
IW2-0102 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 91.2 | 0 | 8
IW2-0102 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 53.3 | 0 | 8
IW2-0103 | Brightfield Electrical — Elec Fit-Out Crew C [Ironwood] | 138.4 | 0 | 8
IW2-0103 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 81.2 | 0 | 8
IW2-0105 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 178.3 | 0 | 8
IW2-0106 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 148.5 | 0 | 8
IW2-0107 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 67.9 | 0 | 8
IW2-0108 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 52.7 | 0 | 8
IW2-0109 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 145.9 | 0 | 8
IW2-0110 | AquaGuard Fire & Plumbing — Plumbing/FP Crew B [Ironwood] | 49.8 | 0 | 8
IW2-0111 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 51.7 | 0 | 8
IW2-0114 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 94.1 | 0 | 8
IW2-0114 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 43.8 | 0 | 8
IW2-0115 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 134.1 | 0 | 8
IW2-0115 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 84.5 | 0 | 8
IW2-0116 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 55.6 | 0 | 8
IW2-0117 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 158.6 | 0 | 8
IW2-0118 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 228.4 | 0 | 8
IW2-0118 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 84.4 | 0 | 8
IW2-0119 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 100.5 | 0 | 8
IW2-0119 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 67.9 | 0 | 8
IW2-0120 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 158.4 | 0 | 8
IW2-0120 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 82 | 0 | 8
IW2-0121 | TechLink Automation — Controls/BMS Crew C [Ironwood] | 184.1 | 0 | 8
IW2-0121 | Pinnacle Commissioning — Commissioning Crew A [Ironwood] | 132.8 | 0 | 8
IW2-0124 | Program Controls — PM Crew B [Ironwood] | 25 | 0 | 8
IW2-0125 | Program Controls — PM Crew B [Ironwood] | 16.8 | 0 | 8
IW2-0126 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 66.8 | 0 | 8
IW2-0127 | Program Controls — PM Crew B [Ironwood] | 55.5 | 0 | 8
IW2-0128 | Meridian QA/QC — QA/QC Crew A [Ironwood] | 90.6 | 0 | 8